BRD Factory-Line Work Procedure

Streamlined Approach for 69 L3 Process BRDs (Feb 2 – Jul 31, 2026)

Executive Summary

Objective: Deliver 69 completed and approved BRDs within 26 weeks using a factory-line approach that maximizes throughput, minimizes analyst downtime, and leverages AI automation.

Key Metrics:

- Total effort available: 4,894 hours

- Total effort required: 4,278 hours (69 BRDs × 62 hours)

- Buffer: 616 hours (~14% contingency)

- Team ramp: 1 analyst (weeks 1-9) → 5 analysts (weeks 10-26)

- Client review cycles: 5 business days per BRD

- Expected throughput: ~4 BRDs/week at full capacity

I. CORE PRINCIPLES

1. Pipeline Philosophy

Treat BRD development as a multi-stage pipeline where multiple BRDs flow through stages simultaneously. While BRD #1 is in client review (5 days), the team works on BRDs #2-6.

2. Zero Downtime Rule

No analyst should ever be "waiting" for client input. Use wait periods productively:

- During workshops (awaiting schedule): Work on other BRDs in drafting/prep stages

- During client review (5 days): Progress 3-5 other BRDs through earlier stages

- During rework cycles: Junior analysts draft new BRDs while senior analysts incorporate feedback

3. AI-Assisted Drafting (Not AI-First Invention)

All first drafts use AI to synthesize and structure information from validated sources: SCE interviews, workshop outputs, repository materials, and ConOps documentation. Human effort focuses on:

- Gathering primary information from SCE stakeholders

- SCE-specific contextualization and validation

- Quality control and accuracy checking

- Client-facing activities (workshops, reviews)

- Complex adaptation requiring domain expertise and judgment

4. Batch Processing

Group related processes to maximize efficiency:

- Workshop batching: Combine 2-3 related L3 processes in single 3.5-hour sessions

- Review batching: Submit 3-5 BRDs simultaneously for client review

- Sign-off batching: Request approval for multiple BRDs from same sponsor

II. ROLE DEFINITIONS & DIVISION OF LABOR

BPD Manager (1,014 hours total)

Primary Responsibilities:

- Internal quality reviews (Step 4 checkpoint)

- Workshop facilitation and client relationship management

- Weekly prioritization and resource allocation

- Escalation handling and complex stakeholder management

- Final sign-off preparation

Time Allocation:

- 30% Internal quality reviews (all 69 BRDs)

- 30% Workshop preparation and facilitation

- 20% Client relationship and governance

- 20% Team coordination and sprint planning

Onshore Analysts (3 total: 1 full-time, 2 starting Apr 6)

Primary Responsibilities:

- As-Is process mapping from client interviews

- Workshop preparation (materials, discussion guides)

- Workshop note capture and post-workshop synthesis

- Complex To-Be flow design requiring deep AMI domain knowledge

- Client-facing rework and comment disposition

- Final formatting and handoff coordination

AI Tools Usage: Moderate (assist with synthesis, formatting, quality checks)

Offshore Analysts (2 starting Apr 6)

Primary Responsibilities:

- AI-assisted first draft generation (all BRD sections)

- Initial To-Be flow drafting from repository patterns

- Bulk requirements extraction and population

- Post-workshop content updates (directed by onshore lead)

- Formatting, consistency checks, and repository management

- Knowledge base maintenance and tagging

AI Tools Usage: Heavy (primary drafting tool for all content generation)

III. SEQUENCING STRATEGY

Phase 1: High-Priority Foundation (Weeks 1-9)

Focus: Meter Asset Management & Mass Deployment L1 groups Rationale: These processes occur chronologically first and have highest dependency downstream

Target BRDs (15 total):

- Plan and Procure Metering Assets

- Receive and inspect delivered assets

- Register devices in asset and head-end systems

- Track warehouse inventory and movements

- Reconcile field inventory and system counts

- Manage Vendor Warranty Claims and Returns

- Manage Meter Refurbishment and Testing Cycles

- Perform New Meter Lot Acceptance Testing

- Manage MIV Data Synchronization & Exception Handling

- Reconcile installation records between systems

- Notify customers of installation schedules

- Assign and execute MIV meter deployment work orders

- Assign and execute utility-owned deployment work orders

- Close MIV work orders and update dashboards

- Communicate completion and follow-up

Resource Plan:

- Week 1-9: BPD Manager + 1 Onshore Analyst

- Throughput: ~1.7 BRDs/week (15 BRDs ÷ 9 weeks)

Phase 2: Core Operations (Weeks 10-18)

Focus: Field Operations & Meter Data Operations L1 groups Rationale: Enable steady-state operations and data flow

Target BRDs (25 total): All processes from:

- Field Operations (10 processes)

- Meter Data Operations (8 processes)

- Remaining Mass Meter Deployment (7 processes)

Resource Plan:

- Full team active (5 analysts + manager)

- Throughput: ~2.8 BRDs/week (25 BRDs ÷ 9 weeks)

Phase 3: Revenue & Customer Experience (Weeks 19-26)

Focus: Customer Engagement & Billing + Grid Operations Rationale: Build on data operations foundation; highest business visibility

Target BRDs (29 total): All processes from:

- Customer Engagement & Billing (20 processes)

- Grid & Outage Management (5 processes)

- Data & Analytics Platform (4 processes)

Resource Plan:

- Full team (5 analysts + manager)

- Throughput: ~3.6 BRDs/week (29 BRDs ÷ 8 weeks)

IV. THE 13-STAGE FACTORY LINE (THREE-PHASE APPROACH)

PHASE 1: PROCESS DESIGN & VALIDATION

Goal: Lock down the validated To-Be process flow
Stages: 1-7
Milestone: ✅ VALIDATED TO-BE PROCESS

STAGE 1: Current State Process Mapping (10 hours → Onshore Lead)

Objective: Document As-Is flow that serves as foundation for To-Be design

CRITICAL PRINCIPLE: We cannot draft an accurate As-Is without first gathering information from SCE. AI assists with synthesis and formatting of information we collect, NOT with creating information we don't have.

Activities:

- Research & Preparation (2 hours - Onshore):

  - Review repository for similar processes from other utilities (for context/comparison only)

  - Pull relevant AMI 1.0 documentation from SCE archives

  - Review process connections table to understand upstream/downstream dependencies

  - Identify 2-3 SCE stakeholders/SMEs who currently execute this L3 process

  - Prepare interview guide with targeted questions:

    - What triggers this process today?

    - What are the main steps you follow?

    - Which systems do you use at each step?

    - Where do things go wrong or take longer than expected?

    - What manual workarounds exist?

    - Who do you hand off to, and what do you give them?

- Stakeholder Interviews (3 hours - Onshore):

  - Conduct 1-2 interviews with SCE SMEs who execute this process

  - Use structured interview guide but allow for natural conversation

  - Capture detailed notes on:

    - Current process triggers and initiating events

    - Step-by-step activities (in the order they actually happen)

    - Decision points and branching logic

    - Systems used (CIS, MDMS, HES, EAM, etc.)

    - Cross-team handoffs and dependencies

    - Pain points, delays, and error-prone areas

    - Manual workarounds and "shadow processes"

    - Exception handling approaches

  - AI Note-Taking Assist: Enable Copilot transcription in Teams meeting for automatic capture

  - Screenshot any system demos or workflow examples shared

- AI-Assisted Synthesis (3 hours - Onshore with AI support): Process:

  - Use interview notes as primary source

  - Reference SCE AMI 1.0 documentation as supporting material

  - Use similar process from another utility for structure reference only

  - Run AI prompt (see Appendix A.1.3: As-Is Process Narrative Synthesis)

  - Review AI output for accuracy against interview notes

  - Fill in any gaps or clarify ambiguities

  - Ensure pain points are prominently captured (these drive To-Be improvements)

Output: As-Is process narrative (1-2 pages) with pain points flagged

- Visio Flow Creation (2 hours - Offshore):

  - Translate synthesized narrative into Visio swimlane diagram

  - Use standard notation (BPMN or SCE standard)

  - Label all systems, roles, and handoffs clearly

  - Add visual callouts for pain points (use red text boxes or icons)

  - Include decision diamonds for branching logic

  - Show both "happy path" and key exception flows

  - Save to repository with naming convention: ASIS_[L3-ID]_[ProcessName]_v1.0.vsdx

- Validation with SMEs (Optional - can be async via email):

  - Send draft As-Is narrative and Visio flow back to interviewed SMEs

  - Ask: "Does this accurately reflect how you execute this process today?"

  - Request corrections within 2 business days

  - Incorporate any clarifications

  - Note: This validation step can happen asynchronously while other BRDs progress, minimizing analyst downtime

Outputs:

- As-Is Visio flow diagram (validated by SCE SMEs)

- As-Is narrative (1-2 pages, based on actual SCE interviews)

- Interview notes/transcription (raw source material)

- Pain points summary (foundation for To-Be improvements)

Quality Check: Manager reviews for:

- Completeness (all interview insights captured)

- Accuracy (reflects SCE's actual process, not idealized version)

- Clarity (understandable to someone not in the interviews)

- Pain points clearly documented (these become To-Be improvement drivers)

STAGE 2: Repository Mining & Solution Requirements Filtering (5 hours - Offshore)

Objective: Create structured first draft with clear flags for SCE validation, and identify relevant solution requirements from SCE's ~3000 requirement library

Activities:

- Draft Section 1.1 - Project Background (1 hour):

  - Pull AMI 2.0 program overview from ConOps

  - Summarize business drivers (aging infrastructure, regulatory requirements, customer experience)

  - Describe how this L3 process fits into overall AMI 2.0 program

  - Source: ConOps, AMI 1.0 lessons learned, program charter

  - Mostly reusable across all BRDs with minor L3-specific tweaks

- Extract Capabilities from Repository (1.5 hours with AI): Run AI prompt (see Appendix A.2.2: Capabilities Extraction from Repository) Process:

  - Input: Requirements from 3 similar AMI processes from other utilities

  - AI extracts and synthesizes 10-15 capabilities

  - Format: "Ability to [verb] [object]"

  - Flag uncertain items with "[VALIDATE WITH SCE]"

  - Review AI output for relevance and alignment with process objective

- Solution Requirements Mapping (2 hours - Offshore with AI):

CRITICAL NEW ACTIVITY: Identify which of SCE's ~3000 solution requirements are relevant to this L3 process

Context: SCE has developed comprehensive solution requirements organized by:

- System-based (~2000): MDMS, HES, DI Hub, Analytics Application

  - Within each system: Organized by capability area (e.g., MDMS meter reading requirements)

- Functional (~1000): Software Baseline, Managed Cloud, Service Requirements, Cyber

Objective: Filter the ~3000 to identify the ~20-50 solution requirements that directly or indirectly support this specific L3 process

Step 3.1: Identify Relevant Systems & Capability Areas (30 min - Onshore quick review)

- Based on As-Is flow from Stage 1, identify which systems are involved

  - Example: "Off-Cycle Billing" process involves CSS, MDMS, HES

- Identify which capability areas are relevant

  - Example: MDMS meter reading, MDMS VEE, HES on-demand reads

- Pull the relevant sections from SCE's solution requirements Excel files

  - Example: Extract MDMS meter reading requirements section, HES on-demand reads section

Step 3.2: AI-Assisted Filtering (1.5 hours - Offshore)

Run AI filtering prompt (see Appendix A.2.1: Solution Requirements Filtering)

Process:

- Input: L3 process details, systems involved, key process steps

- Input: Relevant Excel sections from SCE's solution requirements library

- AI classifies each requirement: Directly Relevant, Indirectly Relevant, or Not Relevant

- Output: Excel table with classification and rationale

Step 3.3: Human Review & Validation (30 min - Onshore)

- Review AI's classification

- Validate DIRECTLY RELEVANT selections (these will be traced to business requirements)

- Spot-check NOT RELEVANT exclusions (ensure we didn't miss anything)

- Create initial groupings by process step or capability theme

- Output: Filtered list of 20-50 relevant solution requirements ready for Stage 3

Why This Matters:

- Ensures business requirements in Stage 3 align with approved solution requirements

- Identifies which solution requirements the SI will use to build this process

- Enables traceability (business requirement → solution requirement)

- Highlights any gaps where business needs exist but solution requirements don't

- Draft Success Criteria from Industry Benchmarks (1 hour with AI): Run AI prompt (see Appendix A.2.2: Capabilities Extraction from Repository) Process:

  - Input: Capabilities from step 2, industry best practices

  - AI generates 8-12 success criteria with measurable thresholds

  - Flags criteria requiring SCE-specific KPIs with [SCE TO DEFINE TARGET]

  - Review for completeness and ensure criteria would prove process is working

- Create Section Templates with Placeholders (0.5 hours): Section 1.3.1 - Sponsorship & Stakeholders:

  - Create table structure: | Role | Name | Title | Department |

  - Add placeholder rows with generic roles:

    - Business Sponsor: [SCE TO PROVIDE]

    - Process Owner: [SCE TO PROVIDE]

    - Key SMEs: [SCE TO PROVIDE]

Section 1.3.4 - Scope:

  - Draft initial In/Out of Scope based on:

    - L3 process definition

    - Process connections table (dependencies)

    - Repository examples

  - Flag boundary uncertainties: [SCE TO CONFIRM]

Section 1.3.5 - Users and Devices:

  - Create empty tables:

| User Type/Persona | Key User Characteristics |
| --- | --- |
| [SCE JOB TITLE - TBD] | [TO BE COMPLETED IN SCE SESSION] |

| Device Type | Key Device Characteristics |
| --- | --- |
| [SCE DEVICE NAME - TBD] | [TO BE COMPLETED IN SCE SESSION] |

  - From As-Is flow (Stage 1): Identify which roles/actors appear

  - Create placeholder for each, flagged for SCE to provide actual titles

Outputs from Stage 2:

- Partial Section 1 draft (~6 pages)

- Capabilities list (10-15 items, some flagged for validation)

- Success criteria list (8-12 items, many with "[SCE TO DEFINE]" targets)

- Filtered solution requirements list (20-50 requirements from SCE's 3000)

- Initial solution requirements mapping (which process steps they support)

- Structured templates for stakeholders, scope, users, devices

- Running list of questions for SCE session

Quality Check: Onshore analyst reviews for:

- Logical flow and professional writing

- Appropriate use of "[VALIDATE WITH SCE]" flags

- Solution requirements filtering is accurate (spot-check 10-15 requirements)

- Questions list is clear and answerable

- Templates are ready for SCE input

STAGE 3: SCE Validation Session (4.4 hours - Onshore)

Objective: Gather SCE-specific information to complete Section 1 accurately

Critical Items Requiring SCE Input:

- ✅ Actual job titles and role names (not generic "Billing Specialist")

- ✅ Specific device types, models, and work environments

- ✅ Actual KPIs, targets, and measurement thresholds

- ✅ Named stakeholders, sponsors, and org structure

- ✅ Scope boundary confirmation and clarifications

- ✅ Validation of capabilities list (add/delete/modify)

Pre-Session Preparation (1.5 hours - Onshore):

- Package Pre-Read Materials (0.5 hours):

  - As-Is flow from Stage 1

  - Draft capabilities list with validation flags

  - Draft success criteria with "[SCE TO DEFINE]" placeholders

  - Questions list

  - Empty templates for users/devices/stakeholders

- Create Session Discussion Guide (0.5 hours):

  - Agenda with time allocations

  - Specific questions organized by topic

  - Space for note capture

  - Show example BRD (the one you uploaded) - especially user/device tables

- Send Pre-Read & Schedule (0.5 hours):

  - Email package to SCE process owner + 1-2 SMEs (2 days before session)

  - Request they bring:

    - Org chart for this process area

    - List of systems/devices their teams use

    - Any existing KPIs or performance metrics

  - Confirm 90-minute session on calendar

SCE Validation Session (1.5 hours - Onshore + SCE Stakeholders):

Attendees:

- Onshore BPD Analyst (facilitator)

- SCE Process Owner or Manager

- 1-2 SCE SMEs who execute this process

- (Optional) BPD Manager for high-priority processes

Session Structure:

Segment 1: Capabilities & Success Criteria Validation (30 min)

Facilitator: "We've drafted 12 capabilities based on similar AMI processes at other utilities. Let's walk through each one and you tell us: keep it, modify it, or remove it. Then we'll capture any missing capabilities."

- Display draft capabilities list on screen

- For each capability:

  - SCE confirms: "Yes, this is in scope" / "No, not for us" / "Modify to say..."

  - Capture exact wording changes

  - Ask: "Why is this important? What's the business driver?" (validates rationale)

- Capture any NEW capabilities SCE identifies

- Note-taking: Use Copilot transcription + manual notes

Facilitator: "Now let's talk metrics. How will you know this process is successful? What are the actual targets or KPIs you'll track?"

- Walk through draft success criteria

- For each "[SCE TO DEFINE TARGET]" placeholder:

  - Ask: "What's the actual threshold?" (e.g., "95% read success rate" or "< 2-minute response time")

  - Capture measurement approach: "How will you measure this?"

- Identify any regulatory or compliance-driven success criteria

- Flag any that are aspirational vs. contractual requirements

Segment 2: Stakeholders & Organizational Structure (15 min)

Facilitator: "Who are the key people involved in governing, executing, or supporting this process?"

- Review SCE org chart (if provided)

- Populate stakeholder table:

  - Business Sponsor (executive accountable for process success)

  - Process Owner (manager responsible for day-to-day operations)

  - Key SME roles (people who execute the work)

- Capture:

  - Full names (if available, otherwise titles)

  - Job titles (exact SCE terminology)

  - Department/organization

  - Role in this L3 process

Segment 3: Users & Devices - THE CRITICAL SECTION (30 min)

Facilitator: "In the As-Is flow we documented, we identified [X] different roles/actors. Let's get the details on each one."

For each User Type identified in Stage 1 As-Is:

Show example from uploaded BRD:

User Type: AMO Billing Specialist

Characteristics: Performs daily billing operations in CSS; initiates off-cycle

billing requests; experienced with register-read workflows, OCR troubleshooting,

and manual read entry; works in office or hybrid environment using standard SCE

workstation and CSS/MDMS portals.

Then ask SCE:

- "What's the actual job title at SCE for this role?"

  - Not "Billing Specialist" — is it "Revenue Operations Analyst II"? "Billing Services Representative"?

  - Capture exact title from HR system if possible

- "What systems do they use day-to-day?"

  - List all applications: CIS, MDMS, CSS, EAM, Salesforce, Excel, etc.

  - Capture version/instance names if relevant (e.g., "SAP ISU" vs. "Oracle CC&B")

- "What devices/equipment do they work with?"

  - Desktop, laptop (specific model/requirements)?

  - VPN requirements?

  - Mobile devices (tablets, smartphones, ruggedized handhelds)?

  - Dual monitors, specialized peripherals?

- "What's their work environment?"

  - Office-based (which location/facility)?

  - Field-based (territory coverage)?

  - Hybrid/remote?

  - Shift coverage (8-5, 24/7, on-call)?

- "What's their proficiency level with technology and these processes?"

  - Expert users who know workarounds?

  - Novice users who need step-by-step guidance?

  - Mix of experience levels?

Repeat for each user type in the As-Is process.

For Device Types (if applicable to this L3 process):

Examples: Smart meters, network relays, field diagnostic tools, vehicles

- "What's the specific device type/model?"

  - Not "smart meter" — is it "Landis+Gyr E350" or "Itron OpenWay Riva"?

- "What are the key technical or environmental characteristics?"

  - Deployment location (pole-mounted, pad-mounted, inside buildings)?

  - Environmental exposure (weather, temperature, physical security)?

  - Power source, communication method, expected lifespan?

Capture in the user/device tables in real-time during the discussion.

Segment 4: Scope Boundary Clarification (15 min)

Facilitator: "We've drafted what we think is in scope and out of scope for this process. Let's validate the boundaries."

- Display draft In/Out of Scope section

- Ask for each boundary item:

  - "Is this accurate?"

  - "Are there edge cases we need to call out?"

  - "Any dependencies on other L3 processes we should document?"

- Capture clarifications and add detail

- Flag any scope items that might need change control discussion

Wrap-Up (5 min)

- Recap key decisions and inputs captured

- Confirm any follow-up items (e.g., "I'll send you the org chart with names")

- Thank participants

- Set expectation: "We'll update the BRD and share Section 1 draft within 2 days for quick validation"

Post-Session Documentation & Updates (1.4 hours - Offshore with Onshore QA):

- Transcription Review & Note Synthesis (0.5 hours - Onshore):

  - Review Copilot transcription

  - Clean up notes, ensure all inputs captured

  - Create decision log (what changed from draft)

  - Flag any follow-up questions

- BRD Section 1 Updates (0.7 hours - Offshore):

  - Section 1.2.1: Update capabilities based on SCE validation (add/delete/modify)

  - Section 1.2.2: Replace all "[SCE TO DEFINE]" with actual KPIs and targets

  - Section 1.3.1: Populate stakeholder table with names, titles, orgs

  - Section 1.3.4: Update scope boundaries with clarifications

  - Section 1.3.5: Populate user and device tables with all SCE-specific details

  - Remove all "[VALIDATE WITH SCE]" flags

- Quick Validation Loop (0.2 hours - Onshore via email):

  - Send updated Section 1 to session participants

  - "Quick check: did we capture everything correctly?"

  - Request confirmation within 24 hours

  - Make any final corrections

Outputs from Stage 3:

- Completed Section 1 of BRD (8-10 pages) with accurate SCE-specific content

- Final capabilities list (validated, 10-15 items)

- Final success criteria with actual KPIs and targets (8-12 items)

- Populated stakeholder table with names and titles

- Validated scope boundaries

- Accurately populated user and device tables with SCE job titles, systems, and characteristics

- Decision log documenting what changed from draft

Quality Check: Onshore analyst validates:

- All "[VALIDATE WITH SCE]" and "[SCE TO DEFINE]" flags removed

- User/device tables use exact SCE terminology (not generic placeholders)

- Success criteria include actual measurable targets

- Stakeholder names and titles are accurate

- Content ready for use in Stage 3 (To-Be design and requirements)

STAGE 4: To-Be Process Design (7 hours - Onshore with AI)

Objective: Create and validate the To-Be process flow BEFORE generating requirements

CRITICAL DESIGN PRINCIPLE: The To-Be flow is the foundation for user journeys and business requirements. Generating requirements from an unvalidated To-Be flow leads to massive rework when the flow changes after workshop. This stage validates the To-Be flow first, creating a stable foundation for requirements generation in Stage 8.

Why This Two-Phase Approach:

- User journeys map to specific process steps → if steps change, journeys must be rewritten

- Business requirements support specific workflows → if workflow changes, requirements must be rewritten

- Validating flow early prevents cascading rework downstream

- Focused workshop on process only is more productive than trying to validate process AND requirements simultaneously

Activity 1: To-Be Flow Design (4 hours - Onshore with AI assist)

Objective: Redesign As-Is process to leverage AMI 2.0 capabilities and address pain points

Foundation: At this point we have:

- Validated As-Is flow from Stage 1

- Filtered solution requirements from Stage 2 (showing what systems can do)

- Validated capabilities and success criteria from Stage 3

Process:

- Review As-Is pain points from Stage 1 interviews (15 min)

- Review filtered solution requirements from Stage 2 showing available AMI 2.0 capabilities (15 min)

- Run AI prompt to generate To-Be process design (see Appendix A.4.1: To-Be Process Design from As-Is) (2 hrs)

- Review AI output for quality (1 hr):

  - Verify every automation claim is backed by solution requirement

  - Ensure all As-Is pain points are addressed

  - Validate exception handling is defined

  - Confirm improvement metrics are realistic

- Refine narrative and create initial Visio flow (1 hr - can be offshore)

Output:

- To-Be process narrative (2-3 pages) with numbered steps

- Summary of key changes vs. As-Is

- List of pain points addressed with solution requirement references

- Draft Visio flow showing automated vs. manual steps

Process:

- Run AI prompt to generate initial To-Be narrative (1.5 hrs)

- Validate against AMI 2.0 technical architecture and solution requirements (1 hr)

- Ensure every automation claim is backed by a solution requirement (0.5 hrs)

- Create updated Visio swimlane diagram (1 hr - use offshore if available, otherwise onshore)

  - Standard BPMN notation

  - Label all systems, roles, and handoffs clearly

  - Show both "happy path" and key exception flows

  - Add callouts showing improvements vs. As-Is (e.g., "Was 45 min → Now 2 min")

  - Use green highlighting for automated steps, yellow for manual steps

- Document improvement rationale and expected benefits

Output:

- To-Be Visio flow diagram (draft)

- To-Be narrative (6-10 steps)

- Summary of changes vs. As-Is

- List of automation improvements with supporting solution requirements

- Flagged gaps (desired automations without solution requirement support)

Activity 2: Prepare for Process Validation Workshop (3 hours - Onshore)

Objective: Create focused workshop materials for validating To-Be flow (NOT requirements yet)

Workshop Deck Structure (8-10 slides):

Slide 1: Agenda

- Purpose: Validate To-Be process flow

- Duration: 90 minutes

- Next steps: Requirements workshop in 1 week (after flow is validated)

Slide 2: As-Is Recap

- High-level As-Is flow (simplified diagram or 5-6 bullet points)

- Current pain points (top 5)

- Current cycle time and accuracy metrics

Slides 3-6: To-Be Process Walkthrough (1 slide per 2-3 steps)

- Step-by-step To-Be process

- Highlight what's automated vs. manual

- Show system interactions

- Callout major changes from As-Is

- Note: Keep visual and easy to follow

Slide 7: Key Changes Summary

| What's New | What's Eliminated | What's Automated | Expected Benefit |
| --- | --- | --- | --- |
| Real-time MDMS integration | Manual MDMS lookups | Read retrieval and validation | 45 min → 2 min |
| Auto-ingestion in CSS | Manual data re-entry | Response handling | Zero transcription errors |
| [etc] | [etc] | [etc] | [etc] |

Slide 8: Exception Handling

- What happens when MDMS fails?

- What happens when read is unavailable?

- Manual override capabilities

- Escalation paths

Slide 9: Comparison Metrics

| Metric | As-Is | To-Be | Improvement |
| --- | --- | --- | --- |
| Cycle time | 2 hours | 10 minutes | 92% reduction |
| Manual steps | 8 steps | 2 steps | 75% reduction |
| Error rate | ~5% | <1% | 80% reduction |
| [etc] | [etc] | [etc] | [etc] |

Slide 10: Open Questions & Discussion

- List any areas where team is uncertain

- Note any gaps (desired automation without solution requirement)

- Confirm next steps

Pre-Workshop Actions:

- Send deck to SCE participants 2 days in advance

- Include: "Please review To-Be flow and come prepared to validate each step"

- Request: "Please bring examples of edge cases or exceptions we should consider"

- Set expectation: "This session validates the PROCESS. Next session will cover detailed REQUIREMENTS."

Output:

- Process validation workshop deck (8-10 slides)

- Discussion guide for facilitator

- Pre-read email sent to participants

Activity 3 - Draft Business Assumptions (1 hour - Onshore):

Objective: Document assumptions that underpin the To-Be design to be validated in Stage 5 review

Process:

- Review To-Be flow and identify dependencies on external factors

- Document technology assumptions (system capabilities, integration availability)

- Document organizational assumptions (staffing, training, change readiness)

- Document timeline assumptions (vendor delivery dates, deployment windows)

- Flag assumptions requiring client validation with [VALIDATE WITH SCE]

Assumption Categories:

Technology Assumptions:

Example: "MDMS will support real-time read requests with <2 min response time per MDMS-REQ-047"

Example: "CSS-MDMS interface will be operational by Release 1 deployment (June 2026)"

Organizational Assumptions:

Example: "Billing & Systems team will have 2 FTEs trained on new off-cycle process by go-live"

Example: "Field Ops will accept automated BPEM work orders from CSS without manual verification"

Process Assumptions:

Example: "Account status validation will occur before read request to prevent reads on closed accounts"

Example: "Manual override capability will remain available for supervisor-approved exceptions"

Timeline Assumptions:

Example: "Solution requirements freeze occurs 3 months before Release 1 deployment"

Example: "Testing environment available 2 months before go-live for UAT"

Dependencies Assumptions:

Example: "L3 Process 'Manage Customer Account Changes' will provide account status updates to CSS"

Example: "Meter installation completion triggers account activation workflow"

Format: Create "Section 1.3.6: Business Assumptions" table:

| Assumption ID | Assumption Statement | Category | Impact if Invalid | Validation Status |

| ASMP-001 | MDMS supports <2 min read response | Technology | Process exceeds 10-min target | [VALIDATE WITH SCE] |

| ASMP-002 | Billing team has 2 FTEs trained by go-live | Organizational | Manual fallback required | [VALIDATE WITH SCE] |

Quality Check:

- Each assumption is testable/verifiable

- Impact if invalid is clearly stated

- Assumptions flagged for client validation in Stage 5 review

- Assumptions that affect multiple processes are identified

Outputs from Stage 4:

- Draft To-Be Visio flow

- To-Be narrative

- Process validation workshop deck

- Draft business assumptions (Section 1.3.6) with validation flags

- Foundation ready for Stage 5 Manager QA

Quality Check (Onshore - included in Activity 1 & 2 time):

- Every automation has supporting solution requirement

- No invented capabilities not in solution requirements

- Flow addresses all As-Is pain points

- Flow is logical and complete

- Workshop deck tells clear story

STAGE 5: Manager Review - Process Flow (1 hour - Manager Review)

Objective: Quality gate for To-Be flow BEFORE workshop

FOCUS: This review is ONLY on the To-Be process flow, not the complete BRD. We validate the process design before investing time in requirements generation.

Manager Review Checklist:

Process Flow Quality:

- To-Be flow addresses all As-Is pain points identified in Stage 1

- To-Be flow aligns with AMI 2.0 capabilities from filtered solution requirements

- To-Be flow is logical and complete (no missing steps, no gaps in handoffs)

- Process improvements are realistic and implementable

- Decision points are clear (if/then logic makes sense)

- Exception handling is defined (what happens when automation fails)

- Manual steps that remain are justified and necessary

Automation Validation:

- Every automated step is backed by a solution requirement

- No invented capabilities (all automation claims reference actual solution requirements)

- Appropriate balance between automation and human oversight

- Manual override/fallback options exist for critical steps

Alignment with Program Goals:

- Flow supports success criteria from Section 1.2.2

- Expected benefits are quantified (time saved, errors reduced)

- Cycle time improvement is realistic based on solution requirements

- Scalability considerations addressed

Workshop Readiness:

- Workshop deck tells clear story

- Visio flow is professional and easy to understand

- Changes vs. As-Is are clearly articulated

- Open questions/gaps are identified for discussion

Risk Identification:

- Flag any high-risk areas for workshop discussion

- Identify dependencies on other L3 processes

- Note any gaps where desired automation lacks solution requirement

- Highlight assumptions that need SCE validation

Business Assumptions Quality:

- All assumptions documented in Section 1.3.6 table format

- Each assumption has clear impact statement ("if invalid, then...")

- Technology assumptions reference specific solution requirements

- Organizational assumptions are realistic (staffing, training, change readiness)

- Timeline assumptions align with project schedule and dependencies

- Assumptions requiring client validation are flagged [VALIDATE WITH SCE]

- High-risk assumptions are identified for early validation in Stage 6 workshop

- No circular logic (assumptions that depend on other assumptions)

Manager Actions:

- Provide feedback to analyst within 4 hours (this is quick turnaround to keep flow moving)

- Identify 2-3 critical areas for workshop focus

- Approve for Process Validation Workshop OR send back for revision

- If sent back: Specific, actionable feedback on what needs to change

Common Issues to Flag:

❌ BAD - Invented automation without solution requirement:

To-Be Step 4: "MDMS automatically validates meter health and schedules preventive maintenance" Problem: No solution requirement supports automated preventive maintenance scheduling

✅ GOOD - Automation backed by solution requirement:

To-Be Step 4: "MDMS returns read with quality flag (actual/estimated/edited) per MDMS-REQ-052, triggering CSS validation rules per CSS-REQ-107"

❌ BAD - Missing exception handling:

To-Be Step 5: "CSS requests on-demand read from MDMS" Problem: What happens if MDMS times out or meter is offline?

✅ GOOD - Clear exception handling:

To-Be Step 5: "CSS requests on-demand read from MDMS (HES-REQ-019). If no response within 5 minutes, route to BPEM queue for field investigation with notification to billing user."

❌ BAD - Vague improvement claim:

"Process will be much faster and more accurate"

✅ GOOD - Quantified improvement:

"Cycle time reduced from 2 hours (As-Is manual lookups) to 10 minutes (To-Be automated retrieval per MDMS-REQ-047), 92% reduction. Transcription errors eliminated via auto-ingestion (CSS-REQ-103)."

Output:

- Approved for Stage 6 (Process Validation Workshop)

- OR Feedback for revision with specific action items

- Workshop focus areas identified

- Validated business assumptions ready for Stage 6 review

STAGE 6: Process Validation Workshop (1.75 hours - Onshore Analyst + Manager)

Objective: Validate To-Be process flow with SCE stakeholders BEFORE generating requirements

CRITICAL FOCUS: This workshop is ONLY about validating the process flow. We are NOT discussing detailed requirements yet. That comes in Session 2 (Stage 10) after the flow is validated.

Why Split into Two Sessions:

- Validating process AND requirements in one session is overwhelming

- Process changes invalidate requirements → better to validate process first

- Shorter, focused session is easier to schedule

- Team can generate higher-quality requirements from validated flow

- Session 2 will be more productive with stable foundation

Pre-Workshop (2 hours - included in Stage 4, Activity 2):

Completed in Stage 4:

- Process validation deck created (8-10 slides)

- Deck sent to SCE participants 2 days in advance

- Expectations set: "This session validates the TO-BE PROCESS FLOW only"

Workshop Session 1 (1.5 hours):

Attendees:

- BPD Manager (facilitator)

- Onshore Analyst (note-taker and scribe)

- SCE Process Owner

- SCE Business Sponsor (optional but recommended)

- SCE SMEs who execute this process (2-4 people)

- SI representative (optional, observer only)

Facilitation Setup:

- Use Teams meeting with Copilot transcription enabled

- Share screen with process validation deck

- Have Visio flow open for reference

- Note-taker captures all feedback in real-time

Segment 1: To-Be Process Validation (60 minutes)

Opening (5 min):

- Recap purpose: "We're here to validate the To-Be process flow design"

- Set expectation: "Next session we'll dive into detailed requirements"

- Review agenda: Process walkthrough → Key changes → Exception handling → Next steps

As-Is Recap (5 min):

- Quick reminder of current state (show Slide 2)

- Confirm pain points: "Are these still the main issues you face?"

To-Be Walkthrough (40 min):

Walk through To-Be flow step-by-step (Slides 3-6):

For each process step:

- Present the step: "In the To-Be process, when [trigger occurs], the system will..."

- Highlight what's different: "This eliminates the current manual lookup that takes 45 minutes"

- Pause for validation: "Does this workflow make sense? Is anything missing?"

- Capture feedback: Note-taker records all comments, questions, concerns

AI Scribe Assist:

Use Copilot to transcribe Teams meeting and generate:

- Action items with owners

- Decisions made (e.g., "Confirmed: CSS will auto-request reads without user clicking 'Submit'")

- Process changes requested (e.g., "Add validation step before routing to billing")

- Open questions flagged for follow-up

- Concerns raised (e.g., "What if MDMS is down during month-end?")

Key Validation Questions to Ask:

- "Does this sequence of steps make sense for how you work?"

- "Are we missing any steps that need to happen?"

- "What edge cases or exceptions should we account for?"

- "Who needs to be involved in [specific step]?"

- "What happens if [system X] is unavailable?"

- "Are there regulatory or policy requirements we need to consider?"

Changes Summary Review (10 min):

- Show Slide 7 (Key Changes Summary)

- Walk through what's new, what's eliminated, what's automated

- Confirm expected benefits are realistic

- Question: "Are these improvements achievable and valuable?"

Segment 2: Exception Handling & Edge Cases (20 minutes)

Exception Handling Review:

- Show Slide 8 (Exception Handling)

- Walk through: "What happens when MDMS fails? When meter is offline? When data is invalid?"

- Validate manual override capabilities

- Confirm escalation paths

Edge Cases Discussion:

- Ask: "What scenarios might break this process?"

- Examples: System outages, data quality issues, unusual customer situations

- Capture: How should process handle each edge case?

Manual Steps Validation:

- Confirm which steps still require human intervention

- Validate why manual steps are necessary

- Ensure manual steps are realistic (staff have time, tools, training)

Segment 3: Business Assumptions Validation (15 minutes)

Assumptions Review:

- Display Section 1.3.6: Business Assumptions table

- Walk through key assumptions (technology, organizational, timeline, dependencies)

- For each assumption, ask: "Is this assumption valid? What needs to change?

Validation Questions:

- We've assumed MDMS will support <2 min read response. Is this realistic?

- We've assumed Billing team will have 2 FTEs trained by go-live. Can you commit to this?

- We've assumed CSS-MDMS interface operational by Release 1. Does timeline align with your plan?

Capture Feedback:

- - Assumptions confirmed → Mark as "VALIDATED"

- - Assumptions invalid → Document correct assumption and impact on To-Be design

- - Assumptions uncertain → Flag for follow-up research with action owner

Risk Identification:

- Which assumptions, if invalid, would fundamentally change the To-Be approach?

- Which assumptions require early validation vs. can be confirmed later?

- Which assumptions affect multiple L3 processes (cross-process dependencies)?

Segment 4: Confirm Changes & Next Steps (10 minutes)

Changes Recap:

- Summarize all requested changes to To-Be flow

- Classify: Minor tweaks vs. major redesign

Change Classification:

MINOR TWEAKS (can incorporate quickly):

- Add a validation step

- Change sequence of 2 steps

- Add an additional notification

- Clarify a decision point

- Impact: Session 2 can proceed in 1 week

MAJOR REDESIGN (need significant rework):

- Fundamental workflow changes

- Different system integration approach

- New process steps that change overall flow

- Removal of core automation

- Impact: Session 2 rescheduled for 2 weeks to allow rework

Decision Point:

- If changes are MINOR → "We'll incorporate these and schedule Session 2 for next week"

- If changes are MAJOR → "We need to redesign and will reschedule Session 2 for 2 weeks"

Set Expectations for Session 2:

- "Next session will cover detailed business requirements"

- "Requirements will be based on this validated To-Be flow"

- "We'll discuss functional requirements, user acceptance expectations, and traceability"

- "Duration: 2 hours"

- "We'll send materials 2 days in advance"

Action Items:

- Confirm who will attend Session 2

- Identify any additional stakeholders needed for requirements discussion

- Set tentative date for Session 2

- Any follow-up research needed before Session 2

Post-Workshop (2 hours - Onshore):

Immediate Actions (30 min):

- Review Copilot transcription

- Clean and organize workshop notes

- Create change log with all requested process modifications

- Classify each change: Add step, Modify step, Remove step, Clarify logic, Add exception handling

Change Log Format:

| Change # | Type | Current To-Be | Requested Change | Rationale | Impact |
| --- | --- | --- | --- | --- | --- |
| 1 | Add Step | [none] | Add validation of account status before requesting read | Prevent reads on closed accounts | Minor - add one step |
| 2 | Modify Step | Step 4: CSS requests read | Add priority flag for urgent requests | Support same-day final bills | Minor - enhance existing step |

Communication (30 min):

- Send workshop summary to all participants within 24 hours

- Include: Decisions made, changes requested, next steps

- Confirm Session 2 date and time

- Thank participants for their input

Begin Stage 7 (Process Flow Refinement) (1 hour):

- Start incorporating changes immediately

- Goal: Have updated flow ready for async validation within 2 days

Outputs from Stage 6:

- Workshop notes with validated To-Be flow feedback

- Change log (all requested process modifications)

- Classification: Minor tweaks vs. major redesign

- Session 2 scheduled

- Foundation for Stage 7 (Process Flow Refinement)

Success Metrics:

- All workshop participants agree on To-Be flow direction

- Changes are clearly documented and understood

- Team knows exactly what to fix before Session 2

- Session 2 date is confirmed

Red Flags (escalate to Manager):

- Fundamental disagreement on process approach

- Major gaps in solution requirements (can't automate as planned)

- Stakeholders request capabilities that don't exist in solution requirements

- Scope creep (trying to solve problems outside this L3 process)

STAGE 7: Process Flow Refinement (3 hours - Offshore with Onshore QA)

Objective: Incorporate workshop feedback to create VALIDATED To-Be flow

CRITICAL MILESTONE: At the end of this stage, we have a VALIDATED To-Be flow that will serve as the stable foundation for requirements generation in Stage 8. No more process changes after this point (unless major issues discovered later).

Activity 1: Update To-Be Flow Based on Workshop Feedback (2 hours - Offshore)

Input: Change log from Stage 6 with all requested modifications

Process Flow Updates:

Step 1: Incorporate Changes in Visio (1 hour)

- Add new process steps as requested

- Modify existing steps based on feedback

- Update decision points and branching logic

- Revise exception handling flows

- Add clarifying annotations or callouts

- Ensure swimlanes correctly show role ownership

- Update visual indicators (green for automated, yellow for manual)

Step 2: Update Process Narrative (1 hour - with AI assist)

Run AI prompt (see Appendix A.7.1: Update To-Be Narrative After Workshop)

Process:

- Input: Current To-Be narrative, change log from Stage 6 workshop

- AI updates narrative to incorporate all workshop changes

- Maintains numbered step format and professional language

- Review AI output for accuracy and logical flow

Activity 2: Validate Changes with Onshore (1 hour - Onshore QA)

Onshore Analyst Review:

Completeness Check:

- All changes from change log incorporated in Visio

- All changes from change log incorporated in narrative

- Visio and narrative are consistent (same steps, same sequence)

- No workshop feedback missed or overlooked

Quality Check:

- Updated flow still addresses all As-Is pain points

- Updated flow still aligns with solution requirements

- Automation claims still backed by solution requirements

- Flow is logical and complete (no new gaps introduced)

- Exception handling is comprehensive

Documentation Check:

- Changes are tracked (can explain what changed and why)

- Improvement rationale updated if changes affect benefits

- Any new gaps flagged (if workshop requests require solution requirements we don't have)

Prepare for Async Validation (30 min):

Create validation email to workshop participants:

Subject: Updated To-Be Flow for [L3 Process Name] - Please Validate

Body:

Hi [Participants],

Thank you for your input in yesterday's process validation workshop. We've incorporated

all the changes you requested into the updated To-Be flow.

CHANGES INCORPORATED:

1. [Change #1 description]

2. [Change #2 description]

3. [Change #3 description]

[etc.]

ATTACHED:

- Updated To-Be Visio flow

- Updated To-Be process narrative

PLEASE REVIEW:

Please review the attached materials and confirm:

✓ All your feedback has been incorporated correctly

✓ The updated flow accurately reflects our discussion

✓ No additional changes are needed

NEXT STEPS:

If the flow looks good, we'll proceed with generating detailed business requirements

based on this validated flow. We'll reconvene in [1 week / 2 weeks] for Session 2 to

review the requirements.

Please respond by [DATE - 24 hours from now] with any concerns or confirmation that

the flow is approved.

Thank you!

[Name]

Send Validation Email:

- Attach updated Visio flow

- Attach updated narrative (PDF)

- Set 24-hour response deadline

- CC Manager for visibility

Activity 3: Async Validation Period (24 hours wait - no analyst time)

Possible Outcomes:

✅ APPROVED (Best Case - 80% of time):

- Participants confirm flow is correct

- Minor clarifications may be requested (address immediately)

- Action: Proceed to Stage 8 (Requirements Generation)

- Milestone: VALIDATED TO-BE FLOW ✓

⚠️ MINOR ADJUSTMENTS (Acceptable Case - 15% of time):

- Small tweaks requested (e.g., clarify wording, adjust one decision point)

- Can be addressed in <1 hour

- Action: Make adjustments, send updated version, get quick confirmation

- Milestone: VALIDATED TO-BE FLOW ✓ (slight delay)

🔴 MAJOR ISSUES (Escalation Case - 5% of time):

- Significant misunderstanding revealed

- Need to rework substantial portions of flow

- Action: Escalate to Manager, assess:

  - Can we address quickly? (1-2 days rework)

  - Do we need another workshop session?

  - Is there a fundamental scope or approach issue?

- Impact: Delay Stage 8 until flow is truly validated

Outputs from Stage 7:

- VALIDATED To-Be Visio flow (approved by SCE stakeholders)

- VALIDATED To-Be process narrative (approved by SCE stakeholders)

- Updated improvement summary (if changes affected expected benefits)

- Any new gaps flagged (if workshop requests require missing solution requirements)

- CRITICAL MILESTONE ACHIEVED: Stable foundation for requirements generation

Quality Metrics:

- % of BRDs where To-Be is approved on first async validation (target: >80%)

- Average time from workshop to validated flow (target: <2 days)

- % of flows requiring major rework after validation (target: <5%)

Handoff to Stage 8:

- Validated To-Be flow is now locked as foundation

- Any future process changes require formal change control

- Team can confidently generate requirements knowing flow won't change

- User journeys and requirements will map to actual confirmed process

Success Criteria:

- All workshop participants have confirmed approval

- Visio and narrative are consistent

- Flow addresses pain points and aligns with solution requirements

- No outstanding questions or concerns

- Ready to generate requirements in Stage 8

PHASE 2: REQUIREMENTS DEVELOPMENT

Goal: Build complete BRD with requirements, traceability, and gap analysis
Stages: 8-11
Milestone: ✅ COMPLETE BRD DRAFT READY FOR CLIENT REVIEW

STAGE 8: Requirements Generation (9.4 hours - Offshore with Onshore QA)

Objective: Generate complete BRD content based on the VALIDATED To-Be flow from Stage 7

CRITICAL CONTEXT: We now have a validated To-Be flow that SCE stakeholders have approved (Stage 7). This is the stable foundation for all requirements, user journeys, and remaining BRD content. The risk of rework is dramatically reduced because the process design is locked.

Foundation at this stage:

- ✅ Validated As-Is flow (Stage 1)

- ✅ Completed Section 1 with SCE-specific details (Stage 3)

- ✅ Filtered solution requirements (Stage 2)

- ✅ VALIDATED To-Be flow (Stage 7) ← Critical difference from old approach!

CRITICAL CONTEXT: Two-Layer Requirements Architecture

This stage produces BUSINESS REQUIREMENTS (Layer 1) that trace to SCE'S SOLUTION REQUIREMENTS (Layer 2):

LAYER 1: Business Requirements (what we create in BRDs)

- Process-focused, business outcome-oriented

- Written from user/stakeholder perspective

- Include fit criteria (measurable acceptance tests)

- ~15-25 requirements per L3 process

- Answer: "What must this process accomplish?"

LAYER 2: Solution Requirements (SCE's existing ~3000)

- System-focused, technical specifications

- Vendor-facing, detailed, testable

- Already vetted through RFP process

- Answer: "What must the systems do?"

TRACEABILITY:

- Each business requirement → traces to → 1 or more solution requirements

- Shows how business needs map to system capabilities

- SI uses both layers: BRDs for business context + solution requirements for implementation

Activities:

Activity 1: User Journey Mapping (2 hours - Offshore with AI)

Objective: Create user journey maps based on VALIDATED To-Be flow

Prerequisites:

- Use actual SCE user types from Section 1.3.5 (captured in Stage 3)

- Use VALIDATED To-Be flow from Stage 7 (workshop-approved)

- Reference workshop notes from Stage 6 for user concerns

AI Prompt: See Appendix A.8. User Journey Mapping"

Process:

- Run AI prompt with validated To-Be flow as input (1.5 hrs)

- Review AI output for accuracy (0.5 hrs)

  - Verify journeys map to actual validated To-Be steps

  - Ensure user types match Section 1.3.5 (actual SCE roles)

  - Confirm scenarios are realistic for this validated process

  - Check that "What to Change" reflects validated To-Be improvements

Output:

- 3-5 user journey scenarios mapping to validated To-Be flow

- Journeys are stable (won't need rework because To-Be is validated)

Activity 2: Business Requirements Generation with Traceability (3.5 hours - Offshore with AI, Onshore QA)

CRITICAL DESIGN PRINCIPLE: Business requirements gathering is an exploratory process that starts with business needs, not a translation exercise from solution requirements.

Step 2.1: Generate Business Requirements from Process Needs (3 hours - Offshore with AI)

Objective: Create 15-25 business requirements based on what the VALIDATED process needs to accomplish - WITHOUT referencing solution requirements yet.

AI Prompt: See Appendix A.8. Business Requirements Generation - Step 2.1A"

Process:

- Run AI prompt with validated To-Be flow as input (2.5 hrs)

- Review AI output for completeness (0.5 hrs)

  - Requirements cover all major validated To-Be steps

  - Mix of system capabilities, process procedures, data quality, integration, exceptions

  - Include manual procedures and organizational requirements

  - 15-25 requirements generated

Output:

- 15-25 business requirements in table format

- Requirements based on business needs (NOT yet traced to solution requirements)

Step 2.2: Trace to Solution Requirements (30 minutes - Offshore with AI)

Objective: Map each business requirement to supporting solution requirements

AI Prompt: See Appendix A.8. Business Requirements Generation - Step 2.1B"

Process:

- Run AI prompt to trace requirements (20 min)

- Onshore QA reviews traceability (10 min)

  - Spot-check 10 traceability mappings for accuracy

  - Validate gap classifications make sense

  - Verify no false positives

Output:

- Business requirements with "Traces To" column completed

- Classification: Fully Covered, Partially Covered, Process Req, Organizational Req, or Gap

Activity 3: User Acceptance Expectations (1 hour - Offshore with AI)

Objective: Generate 8-12 UAEs describing what users expect from their experience

AI Prompt: See Appendix A.8. User Acceptance Expectations"

Process:

- Run AI prompt (45 min)

- Quality check (15 min)

  - UAEs are in user voice ("Users expect...")

  - UAEs describe experience, not technical requirements

  - Appropriate level of need assigned (High/Med/Low)

Output:

- 8-12 User Acceptance Expectations

- Mix of High/Medium/Low level of need

- Ready to populate Section 4.3

Activity 4: Performance Requirements (1 hour - Offshore with AI)

Objective: Generate 5-10 performance business requirements based on validated end-to-end process flow

AI Prompt: See Appendix A.8. Performance Requirements"

Process:

- Run AI prompt (45 min)

- Quality check (15 min)

  - Performance requirements cover timing, throughput, availability

  - Baseline on solution requirements where available

  - End-to-end process timing (not just individual system calls)

Output:

- 5-10 performance business requirements

- Traced to solution requirements where applicable

Activity 5: Gap Analysis and Categorization (0.5 hours - Onshore)

Objective: Review traceability and categorize gaps

Detailed Approach: See Appendix A.8. Gap Analysis"

Process:

- Review traceability from Activity 2, Step 2.2

- Categorize gaps into 5 types:

  - ✅ Fully Covered (60-70%)

  - ⚠️ Partially Covered (10-15%)

  - 🔵 Process Requirements (10-15%)

  - 🔵 Organizational Requirements (5-10%)

  - 🔴 True System Gaps (5-10%)

- Prepare gap summary for Master Requirements Workbook Sheet 7

Output:

- Gap analysis with categorized gaps

- Action plan for each gap type

- Foundation for workshop discussion in Stage 10

Activity 6: Master Requirements Workbook Creation (1 hour - Offshore)

Objective: Create single consolidated Excel workbook with auto-calculated traceability

Detailed Structure: See Appendix A.8. Master Requirements Workbook"

Create: Master_Requirements_[L3-ID]_[ProcessName].xlsx

8 Sheets:

- Sheet 1: Business Requirements (MASTER - editable)

- Sheet 2: Performance Requirements (MASTER - editable)

- Sheet 3: User Acceptance Expectations (MASTER - editable)

- Sheet 4: Solution Requirements (REFERENCE)

- Sheet 5: Traceability Forward (AUTO-CALCULATED)

- Sheet 6: Traceability Reverse (AUTO-CALCULATED)

- Sheet 7: Gap Analysis Summary (AUTO-CALCULATED)

- Sheet 8: Instructions

Process:

- Create workbook structure (30 min)

- Populate Sheets 1-4 with content from Activities 2-4 (20 min)

- Configure formulas for Sheets 5-7 (auto-calculated views) (10 min)

Output:

- Single Master Requirements Workbook

- All requirements and traceability in one maintainable file

- Auto-calculated views eliminate synchronization issues

Activity 7: Populate Remaining BRD Sections (0.4 hours - Offshore)

Sections to Populate:

Section 2.1: Insert VALIDATED To-Be flow (Visio + narrative from Stage 7)

Section 2.2 – User Journeys

Template Instruction: "For each User Type/Persona, use one or more rows to describe associated user journey(s). The As-Is and To-Be process models are key to success and must be available to support this effort."

Instructions

User journeys capture the human experience of the To-Be process. Each journey maps a specific scenario to a specific user type and documents what that person thinks, does, and what needs to change. These are written from the user’s perspective, not the system’s perspective.

Prerequisites:

•  Validated To-Be flow from Stage 7 (the process steps the user will follow)

•  Section 1.3.5 user types with actual SCE job titles and characteristics (from Stage 3)

•  As-Is pain points from Stage 1 interviews (what frustrates users today) WHICH ARE BEING ADDRESSED IN THE TO-BE FLOW (Note: not all pain points identified in Stage 1 will be addressed)

•  Workshop notes from Stage 6 (any user concerns or expectations raised)

Step 1: Identify 3–5 key scenarios from the validated To-Be flow. A scenario is a specific situation where a user type interacts with the process. Focus on: the primary happy-path scenario, 1–2 exception/edge-case scenarios, and any scenario that represents a major change from As-Is.

Step 2: For each scenario, map it to a specific user type from Section 1.3.5.

Step 3: Run the AI prompt below to generate draft user journeys.

Step 4 (Onshore QA): Review AI output to verify that user types match Section 1.3.5 exactly (actual SCE job titles, not generic roles), that user actions align with the validated To-Be steps, that “What to Change” items reflect actual improvements from the As-Is process, and that thoughts/feelings are realistic and grounded in interview insights from Stage 1.

Quality Criteria

•  Each journey references a real SCE user type from Section 1.3.5 (exact title)

•  User actions map to actual validated To-Be process steps (not invented steps)

•  "What to Change" items are traceable to As-Is pain points

•  "Why We Need This Change" connects to business drivers or success criteria from Section 1.2

•  Thoughts/feelings are realistic (not aspirational marketing language)

•  Minimum 3 scenarios; maximum 5 per L3 process

AI Prompt – A.S2.1: User Journey Generation

I need to create User Journey Maps for BRD Section 2.2. L3 PROCESS: [Process Name] VALIDATED TO-BE PROCESS FLOW (from Stage 7): [Paste the complete validated To-Be narrative with numbered steps] USER TYPES FROM SECTION 1.3.5: [Paste the user types table with SCE job titles and characteristics] AS-IS PAIN POINTS (from Stage 1 interviews): [List the top 5-7 pain points identified by SCE SMEs] WORKSHOP FEEDBACK (from Stage 6, if relevant): [Any user concerns or expectations raised during the process validation workshop] TASK: Generate 3-5 User Journey scenarios using this exact table format: ¦ Scenario to Be Addressed ¦ User Type/Persona ¦ What is the user thinking or feeling? ¦ What is the user’s action? ¦ What do we want to change about this scenario? ¦ Why do we need this change? ¦ REQUIREMENTS: 1. Use EXACT SCE job titles from Section 1.3.5 (not generic roles) 2. User actions must map to actual To-Be process steps (reference step numbers where possible) 3. Include at least: - 1 primary happy-path scenario (most common use case) - 1 exception-handling scenario (what happens when something fails) - 1 scenario highlighting a major improvement from As-Is 4. "What is the user thinking or feeling?" should include: - Specific system needs (e.g., "I need MDMS to return reads within 2 minutes") - Data accuracy concerns (e.g., "I need to trust the read quality code") - Process efficiency expectations (e.g., "I shouldn’t have to re-enter data manually") - Frustrations being resolved (reference As-Is pain points) 5. "What is the user’s action?" should be a numbered list of specific actions the user takes in the To-Be process 6. "What do we want to change?" must reference specific To-Be improvements (e.g., "Eliminate manual MDMS lookup by using auto-retrieval per Step 4 of To-Be flow") 7. "Why do we need this change?" should connect to business drivers: time savings, error reduction, compliance, user satisfaction FORMAT each user journey as a separate table row with bullet points inside each cell for readability. EXAMPLE (for reference structure only, do NOT copy content): Scenario: Performing an off-cycle meter read for billing purposes User: AMO Billing Specialist Thinking: "I need the read returned quickly so I can finalize this bill before the customer calls back" / "I need to know if this is an actual or estimated read" Action: 1. Log into CSS 2. Navigate to account 3. Initiate read request 4. Review returned read with quality code 5. Apply to bill Change: Eliminate 45-minute manual MDMS lookup; auto-ingest reads with quality codes directly into CSS Why: Reduce cycle time from 2 hours to 10 minutes; eliminate transcription errors; improve customer satisfaction

3. Section 2.3 – Detailed User Type Characteristics

Template Instruction: "Complete table to provide additional details about user types. The As-Is and To-Be process models are key to success and must be available to support this effort."

Instructions

This section creates a matrix showing which tasks each user type performs and how frequently. Unlike Section 1.3.5 (which captures who users are and their general characteristics), Section 2.3 captures what specific tasks they perform within this L3 process and how often.

Prerequisites:

•  Section 1.3.5 user types (from Stage 3) – actual SCE job titles and characteristics

•  Validated To-Be flow from Stage 7 – the process steps that define tasks

•  User journeys from Section 2.2 – what actions each user takes

Step 1: Extract 8–12 discrete tasks from the validated To-Be flow. These become the column headers in the characteristics matrix. Tasks should be action-oriented (e.g., "Initiate Read Request," "Validate Read Quality," "Approve Exception Override").

Step 2: Run the AI prompt below to generate the draft matrix.

Step 3 (Onshore QA): Verify that tasks align with actual To-Be steps, that user types match Section 1.3.5, that Y/N assignments are logical (e.g., a field technician shouldn’t be approving billing exceptions), and that frequency designations are realistic based on interview insights.

Quality Criteria

•  Column headers are specific tasks derived from the To-Be flow, not generic activities

•  User types exactly match Section 1.3.5 (SCE job titles)

•  Each user type has at least 2 tasks marked "Y"

•  No task is assigned to zero users (every task has an owner)

•  Frequency values are realistic: Multiple Times per Session, Daily, Weekly, Monthly, As Needed

•  Task descriptions in the first column are specific enough to differentiate from other L3 processes

AI Prompt – A.S2.2: User Type Characteristics Matrix

I need to create a Detailed User Type Characteristics matrix for BRD Section 2.3. L3 PROCESS: [Process Name] VALIDATED TO-BE PROCESS FLOW (from Stage 7): [Paste the complete validated To-Be narrative with numbered steps] USER TYPES FROM SECTION 1.3.5: [Paste the user types table with SCE job titles and characteristics] USER JOURNEYS FROM SECTION 2.2: [Paste the user journey table just completed] TASK: Create a User Type Characteristics matrix with the following structure: ¦ User Type ¦ Tasks (description) ¦ Frequency ¦ [Task 1] ¦ [Task 2] ¦ ... ¦ [Task N] ¦ REQUIREMENTS: 1. Extract 8-12 discrete tasks from the To-Be flow steps. - Each task should be a specific action (verb + object) - Use column headers that are 3-5 words max - Example headers: "Initiate Read Request" / "Validate Read Quality" / "Route to Field Ops" / "Approve Exception" / "Close Work Order" 2. Use EXACT SCE job titles from Section 1.3.5 3. For each user type, provide: - Tasks: Brief description of what this user does in this process (1-2 sentences) - Frequency: How often they perform tasks in this process (Multiple Times per Session / Daily / Weekly / Monthly / As Needed) - Y/N for each task column indicating whether this user performs that task 4. Ensure every task has at least one user assigned (Y) 5. Ensure every user has at least two tasks assigned (Y) 6. Mark with "?" any assignment you are uncertain about (flag for SCE validation) OUTPUT FORMAT: Provide as a formatted table ready for insertion into the BRD.

4. Section 2.4 – Business Constraints

Template Instruction: "Describe all constraints from a business perspective which apply to the system and why they exist. Performance, response time, availability, and system capacity often top the list."

Instructions

Business constraints are limitations or boundaries that the To-Be process must operate within. These are NOT requirements (which describe what the system must do), but rather the conditions and restrictions that shape how the process and system can operate. Think of constraints as the guardrails.

Prerequisites:

•  Validated To-Be flow from Stage 7

•  Filtered solution requirements from Stage 2 (contain performance/capacity specs)

•  SCE interviews from Stage 1 (capture operational realities)

•  Success criteria from Section 1.2.2 (contain performance targets)

•  As applicable, ConOps documentation (regulatory and program-level constraints)

Step 1 (Onshore Lead): Review the following sources to identify constraints: regulatory requirements (CPUC mandates, tariff schedules, data retention rules), operational availability windows (maintenance blackouts, peak billing cycles, month-end close periods), system integration constraints (API rate limits, batch processing windows, data latency), budget or resource constraints referenced in ConOps, and any SCE-specific policies mentioned in Stage 1 interviews.

Step 2: Run the AI prompt to generate a structured constraints table.

Step 3 (Onshore QA): Review for completeness and accuracy. Constraints should be specific and verifiable, not vague. Every constraint should have a clear reason for existing.

Common Constraint Categories for AMI Processes

The following categories should be considered for every L3 process. Not all will apply, but each should be evaluated:

| Category | Examples | Typical Source |
| --- | --- | --- |
| Regulatory / Compliance | CPUC data retention mandates, tariff schedule deadlines, customer notification requirements | ConOps, CPUC filings |
| Operational Availability | 24/7 meter data collection, business hours only for manual steps, month-end billing blackout | SCE interviews, IT policy |
| System Performance | MDMS response time SLAs, HES concurrent read limits, batch processing windows | Solution requirements |
| Data Quality / Integrity | Read validation thresholds, VEE rule tolerances, audit trail requirements | Solution requirements, ConOps |
| Integration / Interoperability | API rate limits, batch vs. real-time constraints, legacy system compatibility during AMI 1.0/2.0 coexistence | Solution requirements, technical architecture |
| Security / Access | Role-based access requirements, data encryption mandates, audit logging | Cyber requirements, SCE IT policy |
| Budget / Resource | Staffing limitations, training timeline constraints, phased deployment schedule | Program charter, ConOps |

AI Prompt – A.S2.3: Business Constraints Generation

I need to create a Business Constraints table for BRD Section 2.4. L3 PROCESS: [Process Name] VALIDATED TO-BE PROCESS FLOW (from Stage 7): [Paste the validated To-Be narrative] SOLUTION REQUIREMENTS (filtered from Stage 2): [Paste the filtered solution requirements relevant to this process] SUCCESS CRITERIA FROM SECTION 1.2.2: [Paste success criteria with KPIs and targets] SCE-SPECIFIC CONTEXT (from Stage 1 interviews and ConOps): [Paste any regulatory requirements, operational policies, system limitations, or organizational constraints mentioned by SCE] AMI 1.0/2.0 COEXISTENCE CONTEXT: [Note any constraints related to the 4-5 year migration period where both legacy and new systems must operate simultaneously] TASK: Generate a Business Constraints table with 8-15 constraints. OUTPUT FORMAT: ¦ Business Constraint ¦ Description ¦ REQUIREMENTS: 1. Each constraint must have a clear, specific description (not vague) 2. Each description must explain WHY the constraint exists 3. Include constraints from these categories (where applicable): - Regulatory/Compliance (CPUC mandates, tariff deadlines) - Operational Availability (system uptime, processing windows) - System Performance (response times, throughput limits) - Data Quality/Integrity (validation thresholds, audit requirements) - Integration (API limits, batch windows, legacy coexistence) - Security/Access (role-based access, encryption) - Budget/Resource (staffing, training, phased deployment) 4. Do NOT include constraints that are actually requirements in disguise. A constraint is a LIMITATION, not a CAPABILITY. - BAD: "System must process 100K reads per hour" (this is a requirement) - GOOD: "Batch processing window is limited to 11pm-5am due to system maintenance schedules, constraining the volume of reads that can be reprocessed outside of real-time operations" 5. Flag any constraint you are uncertain about with [VALIDATE WITH SCE] 6. For AMI 2.0 migration: include at least one constraint related to the coexistence period (both AMI 1.0 and 2.0 running simultaneously)

5. Section 2.5 – Business User Environment

Template Instruction: "Describe the operating parameters and conditions that the proposed solution must operate under, and how the proposed solution interacts with the existing and external systems. Also describe any special consideration as it relates to the operating environment and the expected physical environment in which the solution will be deployed."

Instructions

This section describes the operational environment where the To-Be process will run. It covers both the physical environment (where users work, what hardware they use) and the system environment (how the solution integrates with existing SCE systems). Most of this content comes directly from Section 1.3.5 user/device tables and the solution architecture from ConOps.

Prerequisites:

•  Section 1.3.5 user and device tables (from Stage 3) – work environments, hardware, systems

•  To-Be flow from Stage 7 – which systems are involved

•  As available, SCE technical architecture documentation (ConOps, solution design)

•  Filtered solution requirements from Stage 2 – system interactions

Step 1 (Onshore): This section is primarily a narrative synthesis of information you already have. Write 2–4 paragraphs covering:

Paragraph 1 – Physical User Environment: Describe where users work (office, field, hybrid, remote), what hardware they use (desktops, laptops, ruggedized tablets, mobile devices), network connectivity (on-premises LAN, VPN, cellular), and shift patterns (business hours, 24/7, on-call). Source this directly from Section 1.3.5 user characteristics.

Paragraph 2 – System Environment: Describe the key systems involved in this process (from the To-Be flow) and how they interact. Reference the solution architecture: MDMS, HES, CSS, EAM, DI Hub, Analytics Platform, etc. Note whether integrations are real-time API, batch, or message-based. Reference relevant solution requirements for integration specifics.

Paragraph 3 – Coexistence Environment: Describe the AMI 1.0/2.0 coexistence situation for this process. During the 4–5 year migration, this process may need to handle both legacy AMI 1.0 meters (via legacy head-end systems routing through new MDMS) and new AMI 2.0 meters (native to new systems). Explain how this process operates in both modes.

Paragraph 4 – Special Considerations: Note any special environmental conditions: field deployment conditions (weather exposure, physical security), data center requirements, disaster recovery considerations, or geographic coverage areas.

No dedicated AI prompt is provided for this section because it is a direct narrative synthesis of existing content from Section 1.3.5, the To-Be flow, and ConOps. However, if an analyst prefers AI assistance, use the general-purpose synthesis prompt below.

AI Prompt – A.S2.4: User Environment Synthesis (Optional)

I need to write the Business User Environment section (Section 2.5) for a BRD. Synthesize the following inputs into 3-4 professional paragraphs. L3 PROCESS: [Process Name] USER TYPES AND THEIR ENVIRONMENTS (from Section 1.3.5): [Paste the full user types table including work environment, hardware, systems, and shift information] DEVICE TYPES (from Section 1.3.5, if applicable): [Paste the device types table] SYSTEMS IN TO-BE FLOW: [List the systems involved in this process: e.g., CSS, MDMS, HES, EAM, Salesforce] INTEGRATION APPROACH: [Note whether integrations are real-time API, batch, message queue, etc. from solution requirements or ConOps] AMI 1.0/2.0 COEXISTENCE NOTES: [Describe how this process handles both legacy and new meters during the migration period] TASK: Write 3-4 paragraphs covering: 1. Physical user environment (where users work, hardware, connectivity) 2. System environment (key systems, integrations, data flows) 3. Coexistence environment (AMI 1.0/2.0 dual operation during migration) 4. Special considerations (if applicable: field conditions, DR, security) Use professional utility-industry language. Be specific about SCE’s environment (use actual system names, job titles, and locations). Do not include information you don’t have – flag gaps with [SCE TO CONFIRM].

6. Section 2.6 – Business Assumptions & Dependencies

Template Instruction: "Describe the assumptions and conditions upon which the requirements depend. Describe the transition and future state that’s expected to be present when the solution is deployed."

Instructions

Assumptions are things the team believes to be true for the purposes of designing this process, but that have not been formally confirmed. Dependencies are external conditions or deliverables that must be in place for this process to work as designed. Both are critical for managing risk: if an assumption proves false or a dependency is not met, the To-Be process design may need to change.

Prerequisites:

•  Validated To-Be flow from Stage 7 – the process design that assumptions support

•  Filtered solution requirements from Stage 2 – system capabilities assumed

•  As applicable, ConOps and program timeline – deployment sequencing and release planning

•  Workshop notes from Stage 6 – any assumptions discussed or flagged

Step 1: Identify assumptions that underpin the To-Be design. Good assumptions answer: "What must be true for this To-Be process to work as designed?" Common sources include: system capabilities assumed from solution requirements, organizational readiness (training, staffing, change management), data quality and availability, integration partner readiness (SI, MIV vendors), and regulatory/policy stability.

Step 2: Identify dependencies by reviewing the process connections table and ConOps. Dependencies answer: "What external deliverables or conditions must be in place?" Common sources include: upstream L3 processes that feed into this one, system deployments or releases that must be completed first, data migrations or conversions that must be done, training or organizational changes required, and third-party vendor readiness.

Step 3: Run the AI prompt below to generate structured assumptions and dependencies.

Step 4 (Onshore QA): Review for completeness, accuracy, and risk relevance. Every assumption should be something that, if false, would require process redesign. Every dependency should be something that, if missing, would block this process from operating.

Quality Criteria

•  Minimum 8 assumptions and 5 dependencies per L3 process

•  Each assumption states what is believed to be true AND the consequence if it is not true

•  Each dependency identifies the external deliverable AND which process step it supports

•  Dependencies reference specific upstream L3 processes by name (from the process hierarchy)

•  AMI 1.0/2.0 coexistence assumptions are explicitly documented

•  No assumption contradicts a validated solution requirement

AI Prompt – A.S2.5: Assumptions & Dependencies Generation

I need to create Business Assumptions and Dependencies for BRD Section 2.6. L3 PROCESS: [Process Name] VALIDATED TO-BE PROCESS FLOW (from Stage 7): [Paste the validated To-Be narrative with numbered steps] FILTERED SOLUTION REQUIREMENTS (from Stage 2): [Paste the directly relevant solution requirements for this process] PROCESS CONNECTIONS (upstream/downstream): [List L3 processes that feed into or receive output from this process] Example: - Upstream: "Register devices in asset and head-end systems" must complete before this process can retrieve reads from the device - Downstream: "Calculate TOU bills" depends on validated reads from this process PROGRAM CONTEXT: - AMI 2.0 deployment spans 4-5 years with phased meter rollout - During migration, both AMI 1.0 and 2.0 meters operate simultaneously - Legacy head-end systems remain connected during transition - New MDMS is the central data hub for both meter generations WORKSHOP NOTES (any assumptions discussed in Stage 6): [Paste relevant discussion points about assumptions or risks] TASK: Generate two structured tables: TABLE 1: ASSUMPTIONS (minimum 8) ¦ ID ¦ Assumption ¦ Category ¦ Impact if False ¦ TABLE 2: DEPENDENCIES (minimum 5) ¦ ID ¦ Dependency ¦ Source/Owner ¦ Supports To-Be Step ¦ Target Date ¦ REQUIREMENTS FOR ASSUMPTIONS: 1. Each assumption states what is BELIEVED to be true 2. Include "Impact if False" column explaining consequence 3. Categories: System Capability, Data Quality, Organizational Readiness, Integration, Regulatory, Program Timeline 4. Must include at least one assumption about: - AMI 1.0/2.0 coexistence (e.g., "Legacy meters will route data through new MDMS during transition") - System performance (e.g., "MDMS will meet SLA response times per solution requirements") - Organizational readiness (e.g., "SCE staff will be trained on new MDMS interface before Go-Live") 5. Assumptions must not contradict solution requirements 6. Flag uncertain assumptions with [VALIDATE WITH SCE] REQUIREMENTS FOR DEPENDENCIES: 1. Each dependency identifies a specific external deliverable or condition 2. Include which To-Be step depends on this deliverable 3. Include source/owner (which team, vendor, or L3 process is responsible) 4. Include target date or milestone if known (otherwise "[TBD]") 5. Must include upstream L3 process dependencies from the process connections table 6. Must include system deployment dependencies (which releases/systems must be live before this process can operate) DECISIONS: Also list any key decisions made during Stages 3-7 that affect this process design, formatted as: ¦ ID ¦ Decision ¦ Made By ¦ Date ¦ Rationale ¦ If no formal decisions were documented, note: "Formal decisions to be captured during requirements validation (Stage 10)."

Outputs from Stage 8:

- Complete BRD draft (~35-45 pages) based on VALIDATED To-Be flow

- Master Requirements Workbook (Excel) with 8 sheets

- All sections populated with content based on validated process flow

- Foundation ready for Stage 9 (Full BRD Review)

Quality Check (Onshore - 1 hour included in activities above):

- 25% of requirements spot-checked for quality

- Requirements map to validated To-Be steps (minimal rework risk)

- UAEs distinct from business requirements

- Master Requirements Workbook formulas working correctly

- Traceability accurate

- Gap analysis reasonable

- No contradictions with solution requirements

Key Benefit of This Approach: Since requirements are generated from a VALIDATED To-Be flow (Stage 7), there is minimal risk of rework. In the old approach, process changes during the workshop often invalidated requirements and user journeys, requiring significant rework. Now, the process is locked before requirements are generated.

STAGE 9: Manager Review - Full BRD (1 hour - Manager Review)

Objective: Quality gate for complete BRD before Requirements Workshop (Session 2)

CONTEXT: This is the full BRD review. The To-Be flow was already validated in Stage 7, so this review focuses on requirements quality, traceability, and content completeness.

Manager Review Checklist:

Content Completeness:

- All template sections populated (no "[TBD]" placeholders)

- Validated To-Be flow from Stage 7 is embedded (Visio image + narrative)

- Minimum 15 functional business requirements

- Minimum 5 performance business requirements

- Minimum 8 User Acceptance Expectations

- All requirements have fit criteria and rationale

- All UAEs have level of need (High/Med/Low)

- Master Requirements Workbook created with all 8 sheets

- Gap analysis in Sheet 7 is complete

Requirement Quality (sample 10 requirements):

- Each requirement is single, testable statement

- No ambiguous terms ("user-friendly," "efficient," "as needed")

- Fit criteria are objective and measurable

- Requirements describe "what" (outcome), not "how" (design/implementation)

- Proper traceability to capabilities AND solution requirements

- Business requirements are distinct from solution requirements (not just rephrasing)

- Requirements map to validated To-Be process steps

User Acceptance Expectations Quality (sample 5 UAEs):

- UAEs written in user voice ("Users expect that...")

- UAEs describe experience/expectations, not technical specifications

- UAEs are distinct from business requirements (complementary, not redundant)

- Level of need (High/Med/Low) appropriately assigned

- Coverage across key categories (reliability, usability, transparency, automation, exceptions, performance)

Traceability Quality (Master Requirements Workbook):

- Sheet 1: All BRs have entries in "Traces To" column (or flagged as gap)

- Sheet 5: Traceability Forward formulas working, auto-populates from Sheets 1-4

- Sheet 6: Traceability Reverse shows which BRs use each solution req

- Sheet 7: Gap Analysis auto-calculated counts match expectations

- Test formula integrity: Change a BR's traceability in Sheet 1 → verify Sheets 5-7 update

- Spot-check 10 traceability mappings for accuracy

- No business requirement contradicts solution requirement

- Gap analysis is reasonable (process/org requirements vs. true system gaps correctly classified)

SCE Alignment:

- Terminology consistent with ConOps and solution requirements

- Success criteria match program KPIs

- Dependencies on other L3 processes documented

- Release assignments align with IT roadmap

- Requirements support validated To-Be flow (no misalignment)

Formatting:

- Professional appearance

- Consistent heading styles

- Tables properly formatted (especially Master Requirements Workbook)

- Diagrams legible and labeled

- Validated To-Be flow clearly shows improvements vs. As-Is

Workshop Readiness (Session 2):

- Requirements are ready for detailed review

- Traceability can be presented clearly

- Gap analysis ready for discussion

- Open questions identified for workshop

Manager Actions:

- Provide feedback within 4 hours (quick turnaround to keep momentum)

- Identify 2-3 critical requirements areas for Session 2 focus

- Approve for Requirements Workshop (Session 2) OR send back for revision

- If sent back: Specific, actionable feedback

Output:

- Approved for Stage 10 (Requirements Workshop - Session 2)

- OR Feedback for revision with specific action items

- Workshop focus areas identified

STAGE 10: Requirements Validation Workshop (2 hours - Onshore Analyst + Manager)

Objective: Validate business requirements, UAEs, and traceability with SCE stakeholders

CONTEXT: This is Session 2 of the two-part workshop approach. Session 1 (Stage 6) validated the To-Be process flow. Now we validate the requirements that were generated from that validated flow.

Why This Approach Works:

- To-Be flow is stable (validated in Session 1)

- Requirements map to confirmed process steps

- Workshop can focus entirely on requirements without process changes

- Much more productive than trying to validate process AND requirements simultaneously

Pre-Workshop (2 hours - Onshore):

Create Requirements Workshop Deck (15-20 slides) - Key Slides:

- Slide 1: Agenda (Requirements validation, 2 hours)

- Slide 2: To-Be Flow Recap (validated in Session 1)

- Slides 3-6: Top Business Requirements

- Slide 7: User Acceptance Expectations

- Slide 8: Performance Requirements

- Slides 9-10: Traceability Overview

- Slide 11: Gap Analysis Summary

- Slide 12: Open Questions

Pre-Workshop Actions:

- Send deck to SCE participants 2 days in advance

- Attach: Full BRD, Master Requirements Workbook

- Set expectation: "This session validates REQUIREMENTS. Process flow already validated."

Workshop Session 2 (2 hours):

Attendees:

- BPD Manager (facilitator), Onshore Analyst (note-taker)

- SCE Process Owner, Business Sponsor, SMEs (2-4 people)

- SI representative (optional, observer)

Segment 1: Quick Process Recap (10 minutes)

- Recap Session 1 validated flow

- Confirm no major process issues

- Focus on requirements today

Segment 2: Business Requirements Deep Dive (75 minutes)

- Part A: Functional Requirements (45 min) - Walk through top 10-12 requirements

- Part B: User Acceptance Expectations (15 min) - Validate UAEs

- Part C: Performance Requirements (15 min) - Confirm thresholds

Segment 3: Traceability & Gap Review (25 minutes)

- Explain two-layer requirements model

- Show traceability examples in Master Requirements Workbook

- Discuss partially covered requirements and true system gaps

- Classify gaps and resolution approach

Segment 4: Wrap-Up & Next Steps (10 minutes)

- Summarize requested changes

- Confirm gap resolution plan

- Next steps: Refinement (Stage 11) → 5-day review (Stage 12) → Final approval (Stage 13)

Post-Workshop (2 hours - Onshore):

- Review Copilot transcription

- Create requirements change log

- Send workshop summary within 24 hours

- Confirm 5-day review cycle start date

Outputs from Stage 10:

- Workshop notes with requirements feedback

- Requirements change log (with requested modifications)

- Gap resolution decisions

- Foundation for Stage 11 (Requirements Refinement)

STAGE 11: Requirements Refinement (5.8 hours - Offshore with Onshore QA)

Objective: Incorporate workshop feedback into requirements

CRITICAL NOTE: The To-Be process flow is stable (validated in Stage 7). This stage ONLY refines requirements, UAEs, and performance requirements. No process flow changes unless a critical issue was discovered.

Activity 1: Requirements Updates (4 hours - Offshore with AI)

Step 1: Update Business Requirements (2 hours)

- Modify existing requirements per feedback

- Add new requirements requested in workshop

- Remove requirements deemed out of scope

- Update fit criteria if thresholds changed

- Adjust priorities based on workshop discussion

Step 2: Update User Acceptance Expectations (0.5 hours)

- Add new UAEs suggested in workshop

- Modify level of need if feedback indicated different priority

- Remove UAEs if deemed redundant

Step 3: Update Performance Requirements (0.5 hours)

- Adjust timing thresholds based on workshop discussion

- Modify throughput or availability targets if needed

- Add new performance requirements if identified

Step 4: Update Master Requirements Workbook (1 hour)

- Update Sheets 1-3 with all changes

- Sheets 5-7 auto-recalculate (traceability and gap analysis)

- Verify formulas still working correctly

- Update gap analysis if any gaps were resolved or new ones identified

Activity 2: Capabilities & Success Criteria Tuning (1.8 hours - Onshore)

Validate Alignment:

- All updated requirements still trace to capabilities (Section 1.2.1)

- Success criteria still achievable given final requirements

- No capability is orphaned (every capability has supporting requirements)

- No requirement contradicts success criteria

Adjust if Needed:

- If workshop changed requirements significantly, may need to adjust success criteria

- Update expected benefits if cycle time or accuracy targets changed

- Ensure consistency across BRD sections

Outputs from Stage 11:

- Updated BRD with all workshop feedback incorporated

- Updated Master Requirements Workbook (all sheets current)

- Requirements change log with disposition (accepted/modified/rejected)

- Any outstanding issues flagged for client review cycle

Quality Check (Onshore - included in Activity 2 time):

- All workshop changes incorporated correctly

- Master Requirements Workbook formulas still working

- No contradictions introduced

- Traceability still accurate

- Gap analysis reflects workshop decisions

Ready for Stage 12: Client Review & Rework (5-day cycle)

PHASE 3: APPROVAL & DELIVERY

Goal: Secure client approval and deliver final BRD package
Stages: 12-13
Milestone: ✅ APPROVED BRD DELIVERED TO SI

STAGE 12: Client Review & Rework (4.4 hours + 5 days wait → Offshore)

Objective: Formal client review cycle and comment disposition

Client Review Period (5 business days):

- Submit BRD via SharePoint/agreed repository

- Client reviews offline

- Client provides consolidated comments via comment log or track changes

During Wait Time:

- DO NOT IDLE: Progress other BRDs through earlier stages

- Typical pattern: While BRDs 1-3 are in client review, work on drafting BRDs 4-9

Comment Incorporation (4.4 hours - Offshore with AI):

- Comment Triage (1 hour - Onshore):

  - Review all client comments

  - Categorize: Accept / Discuss / Reject

  - Flag any comments requiring manager escalation

  - Create disposition plan

- AI-Assisted Rework (3 hours - Offshore): Process:

  - For each substantive comment, use AI to help craft improved language

  - Run AI prompt for complex revisions (see Appendix A.12.1: Address Client Review Comments)

  - Ensure revisions maintain traceability and professional language

  - Update Master Requirements Workbook if requirements change

- Comment Log Update (0.4 hours - Offshore):

  - Document disposition for each comment

  - Track "Accept," "Revised," or "Discuss" status

  - Prepare responses for "Discuss" items

Outputs:

- Revised BRD with all accepted changes

- Comment disposition log

- List of items for discussion (if any)

Quality Check: Onshore validates all substantive changes

STAGE 13: Finalization & Handoff (4 hours → Onshore)

Objective: Prepare BRD for formal approval and downstream use

Activities:

- Final Formatting (1.5 hours):

  - Apply SCE document template styles

  - Generate table of contents

  - Number all requirements sequentially

  - Insert page numbers and headers/footers

  - Embed all Visio diagrams as high-resolution images

  - Run spell check and grammar review

AI Quality Check:

AI PROMPT:

"Review this BRD for common quality issues:

[Paste sections 4.1 and 4.2]

Check for:

- Duplicate requirement IDs

- Missing fit criteria

- Inconsistent terminology

- Vague language (flag any 'should,' 'user-friendly,' 'efficient')

- Requirements that describe design vs. business need

Provide a checklist of issues found."

- Approval Package Creation (1.5 hours):

  - Add approval signature page (Section 6)

  - Create 1-page executive summary

  - Prepare presentation deck (10 slides) for approval meeting:

    - Slide 1: Process overview

    - Slide 2: Key capabilities

    - Slide 3: To-Be process (high-level)

    - Slide 4-5: Top 10 requirements

    - Slide 6: Success metrics

    - Slide 7: Dependencies and risks

    - Slide 8: Implementation assumptions

    - Slide 9: Next steps (SI handoff)

    - Slide 10: Approval request

- Repository Storage (0.5 hours):

  - Save to SharePoint with naming: BRD_[L3-ID]_[ProcessName]_Final_v1.0.docx

  - Upload To-Be Visio flow: TOBE_[L3-ID]_[ProcessName]_v1.0.vsdx

  - Upload As-Is Visio flow: ASIS_[L3-ID]_[ProcessName]_v1.0.vsdx

  - Upload approval deck

  - Upload Master Requirements Workbook: Master_Requirements_[L3-ID]_[ProcessName]_v1.0.xlsx

  - Update BRD tracker with "Ready for Approval" status

- Handoff Preparation (0.5 hours):

  - Create SI handoff package:

    - BRD (Word) - Business requirements with fit criteria, rationale, and narrative sections (complete process documentation)

    - As-Is flow (Visio) - Current state process diagram

    - To-Be flow (Visio) - Future state process diagram

    - Master Requirements Workbook (Excel) - SINGLE consolidated file containing:

      - Sheet 1: Business Requirements (editable master)

      - Sheet 2: Performance Requirements (editable master)

      - Sheet 3: User Acceptance Expectations (editable master)

      - Sheet 4: Solution Requirements (filtered subset of SCE's 3000)

      - Sheet 5: Traceability Forward (auto-calculated: BR → Solution Reqs)

      - Sheet 6: Traceability Reverse (auto-calculated: Solution Req → BRs)

      - Sheet 7: Gap Analysis Summary (auto-calculated)

      - Sheet 8: Instructions for maintaining the workbook

  - Draft handoff email template:

    - Explain two-layer requirements model

    - Point to Master Requirements Workbook as single source of truth

    - Highlight auto-calculated traceability (Sheets 5-7)

    - Explain how to maintain: "Edit Sheets 1-3, Sheets 5-7 auto-update"

    - Highlight any gaps in Sheet 7 requiring change control discussion

  - Tag for OCM/Business Readiness team

Outputs:

- Final BRD ready for approval

- Approval presentation

- Streamlined SI handoff package (4 artifacts instead of 6):

  - BRD (Word) - Business requirements and process documentation

  - As-Is flow (Visio)

  - To-Be flow (Visio)

  - Master Requirements Workbook (Excel) - Replaces 3 separate files:

    - ✅ Replaces: Requirements table export

    - ✅ Replaces: Traceability matrix

    - ✅ Replaces: Filtered solution requirements

    - ✅ Benefit: Single source of truth, auto-calculated views, no synchronization issues

- Updated tracker

SI Handoff Package Structure:

/08_SI_Handoff_Packages/BRD-[ID]_[ProcessName]/

├── BRD_[L3-ID]_[ProcessName]_Final_v1.0.docx

├── ASIS_[L3-ID]_[ProcessName]_v1.0.vsdx

├── TOBE_[L3-ID]_[ProcessName]_v1.0.vsdx

└── Master_Requirements_[L3-ID]_[ProcessName]_v1.0.xlsx

├── Sheet 1: Business Requirements (EDIT HERE - 15-25 functional reqs)

├── Sheet 2: Performance Requirements (EDIT HERE - 5-10 performance reqs)

├── Sheet 3: User Acceptance Expectations (EDIT HERE - 8-12 UAEs)

├── Sheet 4: Solution Requirements (REFERENCE - 20-50 filtered from SCE's 3000)

├── Sheet 5: Traceability - Forward (AUTO-CALCULATED from Sheets 1-4)

├── Sheet 6: Traceability - Reverse (AUTO-CALCULATED from Sheets 1-4)

├── Sheet 7: Gap Analysis Summary (AUTO-CALCULATED from Sheets 1-4)

└── Sheet 8: Instructions (how to maintain this workbook)

Benefits for SI:

- BRD provides business context and "why this matters"

- Master Requirements Workbook provides:

  - Business requirements (what process must accomplish)

  - Performance requirements (how fast, how many)

  - User acceptance expectations (what users expect)

  - Solution requirements (what systems must do)

  - Automatic traceability (business needs → system capabilities)

  - Automatic gap analysis (what's not covered)

  - Impact analysis (if solution req changes, what's affected)

- Single source of truth eliminates synchronization issues

- Auto-calculated views reduce maintenance burden

- Clear instructions enable SI to maintain as design evolves

Approval Process:

- Schedule approval meeting with business sponsors (30-60 min)

- Present highlights using deck

- Obtain signatures on Section 6

- If approved → handoff to SI and OCM

- If not approved → return to Stage 11 (requirements refinement cycle)

VI. WEEKLY SPRINT CADENCE

Sprint Planning (Mondays, 1 hour)

Participants: BPD Manager + All Analysts

Agenda:

- Review prior week accomplishments (10 min)

  - BRDs completed vs. plan

  - Client feedback received

  - Blockers resolved

- Prioritize current week's work (20 min)

  - Identify which BRDs move to which stages

  - Assign BRDs to analysts

  - Schedule SCE validation sessions (Stage 3) - coordinate calendars for 90-min sessions

  - Schedule client workshops (Stage 6: Process Validation, Stage 10: Requirements Validation)

  - Flag dependencies or resource constraints

- AI/Automation improvements (15 min)

  - Share prompt refinements

  - Discuss quality issues from AI outputs

  - Update knowledge repository

- Risk review (15 min)

  - SCE availability for Stage 3 sessions and workshops

  - BRDs at risk of missing milestones

  - Escalations needed

Output: Weekly sprint board showing:

- Each BRD and current stage

- Analyst assignments

- Client milestones (Stage 3 sessions, workshops, reviews, approvals)

- Blockers and mitigation plans

Mid-Week Check-In (Wednesdays, 30 min)

Participants: BPD Manager + Onshore Lead

Quick pulse check:

- Any BRDs stalled?

- Client responsiveness issues?

- Offshore team questions/blockers?

- Adjust assignments if needed

End-of-Week Metrics (Fridays)

Manager Updates Tracker:

- BRDs completed this week (by stage)

- Cumulative BRDs completed vs. plan

- Hours consumed vs. budget

- Client review cycle times (actual vs. 5-day target)

- Quality metrics:

  - % of BRDs requiring major rework post-workshop

  - % of requirements flagged in internal QA

  - Average requirements per BRD

Dashboard Indicators:

- 🟢 Green: On track (±5% of plan)

- 🟡 Yellow: At risk (>5% behind plan)

- 🔴 Red: Off track (>10% behind, escalation needed)

VII. BATCHING STRATEGIES

Workshop Batching

Objective: Reduce workshop overhead by combining related processes

Batching Rules:

- Same stakeholder audience: Combine processes requiring same SMEs

- Same L2 category: Processes that share context

- Max 3 processes per workshop: Maintains focus and engagement

- Related dependencies: Processes that feed into each other

Example Batch:

- Workshop Session: "MIV Deployment Operations"

- L3 Processes:

  - Assign and execute MIV meter deployment work orders

  - Close MIV work orders and update dashboards

  - Resolve Physical Field Installation Exceptions

- Duration: 3.5 hours

- Stakeholders: AMI Deployment Manager, MIV Vendor Representative, IT Integration Lead

Workshop Deck Structure for Batched Sessions:

- Slides 1-2: Agenda and overview of all 3 processes

- Slides 3-8: Process 1 (As-Is, To-Be, requirements)

- Slides 9-14: Process 2 (As-Is, To-Be, requirements)

- Slides 15-20: Process 3 (As-Is, To-Be, requirements)

- Slides 21-22: Cross-process dependencies

- Slide 23: Wrap-up and next steps

Benefits:

- Reduces total workshop count from 69 to ~25-30

- Provides holistic view of related processes

- Identifies integration issues early

Review Batching

Objective: Submit multiple BRDs simultaneously to maximize client throughput

Batching Strategy:

- Submit in groups of 3-5 BRDs

- Stagger submissions weekly (don't flood client)

- Group by same reviewer/approver when possible

Example:

- Week 12 Submission Batch:

  - BRD 10: Notify customers of installation schedules

  - BRD 11: Assign and execute MIV meter deployment work orders

  - BRD 12: Close MIV work orders and update dashboards

  - Reviewer: AMI Deployment Director

  - Review period: 5 business days (Mar 24-30)

During 5-Day Wait:

- Analysts work on BRDs 13-18 (drafting stage)

- Prepare for next workshop (BRDs 19-21)

- Incorporate feedback from prior batch (BRDs 7-9)

Benefits:

- Keeps client in "review mode" vs. constant context-switching

- Allows team to pipeline work efficiently

- Reduces cumulative wait time

Approval Batching

Objective: Streamline final sign-off process

Approach:

- Schedule monthly "BRD Approval Sessions" with business sponsors

- Present 5-8 BRDs in single 2-hour meeting

- Use executive summary deck (2-3 slides per BRD)

- Obtain signatures for all BRDs in batch

Example Approval Session:

- Meeting: AMI Program Steering Committee

- Date: Last Friday of each month

- BRDs for Approval: All BRDs that completed rework cycle that month

- Format:

  - 10 min per BRD: Present highlights, key requirements, dependencies

  - 5 min per BRD: Q&A

  - Signature collection at end of meeting

Benefits:

- Efficient use of executive time

- Creates accountability and rhythm

- Reduces scheduling overhead

VIII. RESOURCE LOADING & PARALLEL PROCESSING

Capacity Planning Model

Weeks 1-9 (Phase 1): Limited Capacity

- Team: Manager (39 hrs/wk) + 1 Onshore Analyst (42 hrs/wk) = 81 hrs/wk

- Throughput: ~1.7 BRDs/week

- Strategy: Focus on highest-priority processes; build knowledge repository

Weeks 10-26 (Phases 2-3): Full Capacity

- Team: Manager (39 hrs/wk) + 3 Onshore (126 hrs/wk) + 2 Offshore (80 hrs/wk) = 245 hrs/wk

- Throughput: ~4 BRDs/week

- Strategy: Maximize parallelization; offshore handles bulk drafting

Parallel Processing Example (Week 15 - Full Team)

BRD Pipeline Status:

| BRD # | L3 Process | Stage | Owner | Status |
| --- | --- | --- | --- | --- |
| BRD 23 | Aggregate feeder loads | Stage 8: Finalization | Onshore 1 | Approval meeting scheduled |
| BRD 24 | Perform VEE | Stage 7: Rework | Offshore 1 | Incorporating client comments |
| BRD 25 | Execute data acquisition | Stage 6: Post-Workshop | Offshore 2 | Updating flows per workshop |
| BRD 26 | Configure VEE rules | Stage 5: Workshop | Manager + Onshore 2 | Workshop on Thu 3/14 |
| BRD 27 | Detect unassigned usage | Stage 4: Internal Review | Manager | QA in progress |
| BRD 28 | Calculate TOU bills | Stage 3: Drafting | Offshore 1 | Requirements generation |
| BRD 29 | Calculate register bills | Stage 3: SCE Session | Onshore 3 | SCE validation session on Wed 3/13 |
| BRD 30 | Generate e-bills | Stage 2A: Repository Prep | Offshore 2 | Extracting capabilities from repository |
| BRD 31 | Manage billing disputes | Stage 1: As-Is | Onshore 1 | Stakeholder interviews scheduled |
| BRD 32 | Cancel and rebill | Stage 0: Queued | - | Starts next week |

This Week's Focus:

- Manager: Internal review (BRD 27), workshop facilitation (BRD 26), approval presentation (BRD 23)

- Onshore 1: Finalize BRD 23, support workshop prep for BRD 26, As-Is interviews for BRD 31

- Onshore 2: Workshop co-facilitation (BRD 26), post-session updates for BRD 29

- Onshore 3: Facilitate SCE validation session for BRD 29 (Wed), post-session documentation

- Offshore 1: Rework (BRD 24), drafting (BRD 28)

- Offshore 2: Post-workshop updates (BRD 25), repository prep (BRD 30)

Key:

- 🔵 Blue (Stages 1-2A): Information gathering and prep

- 🟢 Green (Stages 2B-6): SCE collaboration and validation

- 🟡 Yellow (Stages 7-8): Rework and finalization

Wait Time Absorption:

- While BRD 26 waits for workshop (scheduled Thu), continue drafting BRDs 28-31

- While BRD 24 waits for client review (5 days), work on BRDs 25-30

- Stage 3 sessions (90 min) scheduled mid-week to maintain flow

IX. QUALITY METRICS & CONTINUOUS IMPROVEMENT

Leading Indicators (Track Weekly)

- Cycle Time by Stage:

  - Target: Stage 1 (10 hrs), Stage 2 (9.4 hrs), Stage 3 (13.4 hrs), etc.

  - Actual: Track real hours spent

  - Variance: Flag if >20% over target

- AI Draft Quality:

  - % of AI-generated requirements accepted without revision

  - Target: >70%

  - Action: If <70%, refine prompts

- Internal QA Pass Rate:

  - % of BRDs passing Manager review on first attempt

  - Target: >80%

  - Action: If <80%, increase onshore pre-review

- Client Workshop Productivity:

  - of requirements validated per workshop hour

  - Target: >5 requirements/hour

  - Action: Improve workshop facilitation if low

Lagging Indicators (Track Monthly)

- Client Rework Rate:

  - % of BRDs requiring major rework after first client review

  - Target: <20%

  - Root cause: Workshop validation gaps or poor requirements quality

- Approval Cycle Time:

  - Days from submission to final sign-off

  - Target: <10 days (5 for review + 3 for rework + 2 for approval)

  - Action: Escalate if client review exceeds 7 days

- Throughput vs. Plan:

  - BRDs completed vs. target by phase

  - Target:

    - Phase 1 (Wk 1-9): 15 BRDs

    - Phase 2 (Wk 10-18): 25 BRDs

    - Phase 3 (Wk 19-26): 29 BRDs

  - Buffer: 616 hours allows ~10 BRD rework cycles

Continuous Improvement Rituals

Bi-Weekly Retrospective (30 min):

- What's working well? (keep doing)

- What's not working? (stop doing)

- What should we try? (experiment)

- AI/Prompt refinements based on output quality

Monthly Knowledge Repository Update:

- Add new high-quality BRDs to reference library

- Tag with keywords for AI retrieval

- Retire outdated or low-quality examples

- Update prompt library with learnings

Quarterly Client Satisfaction Check:

- Survey SCE stakeholders on BRD quality

- Gather feedback on workshop effectiveness

- Identify process improvements

X. RISK MITIGATION

Risk 1: Client Workshop Availability

Symptom: Can't schedule workshops within planned timeline

Mitigation:

- Proactive: Secure stakeholder calendars 4 weeks in advance

- Batching: Combine related processes to reduce total workshop count

- Flexibility: Offer multiple time slots; use "if-then" scheduling

- Escalation: Manager engages Program Director if blockers persist

Contingency:

- Conduct async review (send deck, collect written feedback)

- Schedule shorter focused sessions (90 min vs. 3.5 hours)

- Use offshore time zones for early morning/late evening slots

Risk 2: AI Output Quality Degrades

Symptom: >30% of AI-generated content requires major rework

Root Causes:

- Prompts not specific enough

- Repository examples are poor quality

- Analysts not providing sufficient context

Mitigation:

- Prompt Refinement: Update prompt library based on bad outputs

- Repository Curation: Remove low-quality reference materials

- Training: Onshore analysts coach offshore on better AI prompting

- Human Review: Increase onshore spot-checking to 50% vs. 25%

Contingency:

- Shift more work to onshore analysts (slower but higher quality)

- Engage Copilot support for custom model training

Risk 3: Scope Creep (Out-of-Scope Requirements)

Symptom: Workshops surface requirements outside 69 L3 scope

Mitigation:

- Parking Lot: Clearly document out-of-scope items for future phases

- Traceability: Ensure every requirement links to an in-scope capability

- Change Control: Any new L3 processes require formal scope change

Contingency:

- Escalate to Program Steering Committee

- Trade off: If adding 1 L3 process, which existing one defers?

Risk 4: Team Attrition/Illness

Symptom: Analyst unavailable for >1 week

Mitigation:

- Cross-Training: Each onshore analyst shadows another's BRDs

- Documentation: All work tracked in shared repository

- Redundancy: Manager can step in for critical path items

Contingency:

- Reallocate BRDs among remaining analysts

- Extend timeline using 616-hour buffer

- Engage additional contractor if >2 week absence

Risk 5: Client Review Exceeds 5 Days

Symptom: Client takes 10+ days to review BRDs

Impact: Delays downstream approvals and SI handoff

Mitigation:

- Proactive: Set expectation of 5-day SLA in kickoff

- Reminders: Send gentle reminder on day 4 of review

- Escalation: Manager engages client PMO if exceeding 7 days

Contingency:

- Use wait time productively (draft other BRDs)

- Adjust downstream schedule if pattern emerges

- Batch approvals to catch up (e.g., approve 10 BRDs in one session)

XI. TOOLS & TEMPLATES

Shared Repository Structure (SharePoint)

AMI 2.0 BRD Program/

├── 00_Reference_Library/

│   ├── SCE_Solution_Requirements/

│   │   ├── Master_Solution_Requirements_All_3000.xlsx (complete library)

│   │   ├── MDMS_Requirements.xlsx (~600 requirements)

│   │   ├── HES_Requirements.xlsx (~500 requirements)

│   │   ├── DI_Hub_Requirements.xlsx (~300 requirements)

│   │   ├── Analytics_Requirements.xlsx (~400 requirements)

│   │   ├── Software_Baseline_Requirements.xlsx (~100 requirements)

│   │   ├── Managed_Cloud_Requirements.xlsx (~50 requirements)

│   │   ├── Service_Requirements.xlsx (~30 requirements)

│   │   └── Cyber_Requirements.xlsx (~20 requirements)

│   ├── Other_Utilities_AMI_BRDs/

│   ├── SCE_ConOps/

│   ├── SCE_AMI_1.0_Documentation/

│   ├── Industry_Standards/

│   └── Templates/

│       ├── BRD_Template_v1.0.docx

│       ├── Workshop_Deck_Template.pptx

│       ├── Approval_Deck_Template.pptx

│       └── Master_Requirements_Workbook_Template.xlsx (NEW - with formulas pre-configured)

├── 01_Process_Hierarchy/

│   ├── L1_L2_L3_Inventory.xlsx

│   └── Process_Connections.xlsx

├── 02_As-Is_Flows/

│   └── [69 Visio files]

├── 03_To-Be_Flows/

│   └── [69 Visio files]

├── 04_BRDs_In_Progress/

│   └── [Working drafts by analyst]

├── 05_BRDs_In_Review/

│   └── [Submitted to client]

├── 06_BRDs_Approved/

│   └── [Final signed versions]

├── 07_Workshop_Materials/

│   └── [Decks, notes, recordings]

├── 08_SI_Handoff_Packages/

│   └── [BRD + Visio + Master Requirements Workbook - organized by L3 process]

│       └── BRD-[ID]_[ProcessName]/

│           ├── BRD_Final.docx

│           ├── ASIS_Flow.vsdx

│           ├── TOBE_Flow.vsdx

│           └── Master_Requirements_v1.0.xlsx (CONSOLIDATES 3 previous artifacts)

│               ├── Sheet 1: Business Requirements (editable)

│               ├── Sheet 2: Performance Requirements (editable)

│               ├── Sheet 3: User Acceptance Expectations (editable)

│               ├── Sheet 4: Solution Requirements (reference)

│               ├── Sheet 5: Traceability Forward (auto-calc)

│               ├── Sheet 6: Traceability Reverse (auto-calc)

│               ├── Sheet 7: Gap Analysis (auto-calc)

│               └── Sheet 8: Instructions

└── 09_Tracking/

├── BRD_Master_Tracker.xlsx

├── Solution_Requirements_Usage_Tracker.xlsx (NEW - tracks which solution reqs are used by which L3 processes)

├── Weekly_Sprint_Boards/

└── Metrics_Dashboard.pbix

New Artifact: Solution_Requirements_Usage_Tracker.xlsx

Purpose: Track which of SCE's 3000 solution requirements are mapped to which L3 processes

Structure:

| Solution Req ID | System | Requirement Summary | Used By L3 Processes | Total BR Traces | Status |
| --- | --- | --- | --- | --- | --- |
| MDMS-REQ-047 | MDMS | Return reads <2 min | BRD-015, BRD-022, BRD-031 | 8 business requirements | ✅ Actively Used |
| MDMS-REQ-134 | MDMS | Support 50K concurrent | [NONE] | 0 | ⚠️ Orphaned (no L3 process uses) |
| HES-REQ-019 | HES | On-demand reads | BRD-015, BRD-019, BRD-027, BRD-042 | 12 business requirements | ✅ Actively Used |

Benefits:

- Identifies orphaned solution requirements (approved in RFP but not mapped to any business process)

- Shows heavily-used solution requirements (potential bottlenecks or high-value capabilities)

- Enables impact analysis if solution requirement changes

- Provides program-level visibility into solution requirement coverage

BRD Master Tracker (Excel)

Columns:

| Column | Description | Example |
| --- | --- | --- |
| BRD ID | Sequential number | BRD-001 |
| L1 Process | Top-level category | Meter Asset Management |
| L2 Process | Sub-category | Procure and manage metering assets |
| L3 Process | Specific process | Plan and Procure Metering Assets |
| Priority | Sequencing priority | P1 (High) |
| Assigned Analyst | Current owner | Offshore Analyst 1 |
| Current Stage | Where in 8-stage flow | Stage 3: Drafting |
| Stage Start Date | When entered current stage | 3/10/2026 |
| Target Completion | Planned finish for stage | 3/14/2026 |
| Status | RAG indicator | 🟢 Green |
| Hours Consumed | Actual effort to date | 28.5 |
| Hours Remaining | Estimated effort left | 33.5 |
| Stage 3 Session Date | SCE validation session scheduled/completed | 3/05/2026 |
| Workshop Dates | Process Workshop (Stage 6) / Requirements Workshop (Stage 10) | 3/12/2026 / 3/18/2026 |
| Client Review Start | Submission date | 3/21/2026 |
| Client Review End | Feedback received | 3/28/2026 |
| Approval Date | Final sign-off | - |
| Dependencies | Upstream L3 processes | BRD-002, BRD-003 |
| Notes | Issues, blockers, risks | Waiting on stakeholder availability |

Views:

- Sprint View: Filter by current week's active BRDs

- Analyst View: Filter by assigned analyst

- Phase View: Group by Phase 1/2/3

- Risk View: Filter by 🟡 Yellow or 🔴 Red status

- SCE Session View: Upcoming Stage 3 sessions needing scheduling

SCE Validation Session Materials Checklist (Stage 3)

Pre-Session (2 days before):

- Pre-read package sent to SCE participants

  - As-Is flow from Stage 1

  - Draft capabilities list (with validation flags)

  - Draft success criteria (with "[SCE TO DEFINE]" placeholders)

  - Empty templates for users/devices/stakeholders

  - Example BRD section 1.3.5 (user/device tables) for reference

- Session agenda and discussion guide prepared

- Teams meeting link created and tested

- Request sent to SCE for org chart and system/device lists

- Confirmation of attendees (Process Owner + 1-2 SMEs)

During Session:

- Copilot transcription enabled

- Screen sharing ready (capabilities list, templates)

- Real-time note capture in discussion guide

- Capture exact SCE job titles and system names

- Screenshot any org charts or reference materials shared

- Track action items and follow-ups

Post-Session (within 24 hours):

- Notes cleaned and synthesized from transcription

- Section 1 updated with all SCE inputs

- All placeholders and validation flags removed

- Updated Section 1 sent to participants for quick validation

- Follow-up items logged with owners

Workshop Materials Checklist (Stage 5)

Pre-Workshop (4 hours before session):

- Deck sent to stakeholders (2 days prior)

- Teams meeting link created and tested

- Co-facilitator assigned and briefed

- Parking lot slide prepared for out-of-scope items

- Recording permission obtained from participants

- Backup facilitator identified (if manager unavailable)

During Workshop:

- Copilot transcription enabled

- Dedicated note-taker assigned

- Screenshot key decisions/whiteboard sketches

- Track action items with owners in real-time

- Monitor time per agenda section (stay on schedule)

Post-Workshop (within 24 hours):

- Notes cleaned and sent to participants

- Action items logged with due dates

- Change log created (what's different vs. draft BRD)

- Recording uploaded to SharePoint

- Thank-you email sent with next steps

XII. IMPLEMENTATION ROADMAP

Week 1-2: Onboarding & Setup (Feb 2-13, 2026)

Manager Activities:

- Kickoff meeting with SCE PMO (align on scope, schedule, deliverables)

- Secure access to SCE systems (SharePoint, Teams, ConOps repository)

- Request SCE solution requirements in Excel format (~3000 requirements)

- Set up shared SharePoint structure

- Upload knowledge repository materials (other utilities' AMI docs)

- Upload and organize SCE solution requirements library (MDMS, HES, DI Hub, Analytics, Software, Cyber)

  - Create separate Excel files by system for easier filtering

  - Verify requirement IDs are consistent and traceable

  - Add any missing metadata (system, category, release)

- Configure Copilot custom instructions for team

- Create Master Requirements Workbook template with pre-configured formulas for Sheets 5-7

  - Test formulas work correctly

  - Document formula logic in Sheet 8 (Instructions)

  - Save as reusable template for all 69 BRDs

- Create solution requirements usage tracker (track which solution reqs map to which L3 processes)

- Establish weekly sprint cadence (Mondays 9-10am)

- Create BRD Master Tracker with all 69 L3 processes

- Assign priority sequencing (P1/P2/P3)

Onshore Analyst 1 Activities:

- Review BRD template and example (from upload)

- Study SCE ConOps and AMI 1.0 documentation

- Familiarize with SCE solution requirements structure (understand how they're organized by system and capability)

- Practice AI prompting using prompt library

- Practice solution requirements filtering (pick 1 L3 process, filter relevant requirements from the 3000)

- Practice using Master Requirements Workbook template (populate with test data, verify formulas work)

- Complete 1 pilot BRD (highest priority process) as learning exercise

  - Include Master Requirements Workbook in pilot

  - Test two-layer requirements approach

  - Validate auto-calculated sheets update correctly

- Document lessons learned for team training

Deliverables:

- Shared repository operational with SCE solution requirements library uploaded

- Master Requirements Workbook template (reusable across all 69 BRDs)

- Pilot BRD with completed Master Requirements Workbook (serves as example for team)

- Revised prompt library based on pilot learnings

- Solution requirements filtering workflow validated (confirm 2-hour estimate is realistic)

- Workbook formula validation complete (all auto-calculations working correctly)

Week 3-9: Phase 1 Execution (Feb 16 - Apr 4, 2026)

Target: Complete 15 BRDs (Meter Asset Management + Mass Deployment)

Weekly Rhythm:

- Monday: Sprint planning (prioritize, assign, schedule workshops)

- Tuesday-Thursday: Execution (As-Is mapping, drafting, workshops, reviews)

- Friday: Metrics review, repository updates, retrospective

Milestone Checkpoints:

- Week 5 (Mar 8): First 5 BRDs submitted for client review

- Week 7 (Mar 22): First 5 BRDs approved

- Week 9 (Apr 4): 15 BRDs complete; Phase 1 retrospective

Week 10: Team Ramp-Up (Apr 7-11, 2026)

Onboarding New Team Members:

- 2 Onshore Analysts start

- 2 Offshore Analysts start

- 2-day training on BRD approach, AI tools, SCE context

- Assign each new analyst to shadow 1 existing BRD (learn by doing)

- Pair offshore with onshore for first 2 weeks

Manager Activities:

- Reallocate BRDs across expanded team

- Establish offshore daily stand-up (8am PT to overlap with India)

- Set expectations for communication (Slack for quick questions, email for formal)

Week 11-18: Phase 2 Execution (Apr 14 - Jun 5, 2026)

Target: Complete 25 BRDs (Field Ops, Meter Data Ops, remaining Deployment)

Throughput: ~3 BRDs/week

Batching:

- Submit BRDs in groups of 5 every other week

- Schedule 2-3 workshops per week (batched by topic)

- Monthly approval sessions with business sponsors

Milestone Checkpoints:

- Week 14 (May 2): 10 BRDs from Phase 2 submitted for review

- Week 16 (May 16): First approval session (5-8 BRDs)

- Week 18 (Jun 5): 25 BRDs complete; Phase 2 retrospective

Week 19-26: Phase 3 Execution (Jun 8 - Jul 31, 2026)

Target: Complete 29 BRDs (Customer Engagement, Billing, Grid Ops, Analytics)

Throughput: ~3.6 BRDs/week

Focus Areas:

- Highest business visibility (billing, customer experience)

- Integration complexity (cross-system dependencies)

- Regulatory compliance (net metering, opt-out programs)

Milestone Checkpoints:

- Week 22 (Jul 4): All BRDs in client review or later

- Week 25 (Jul 25): Final approval session (remaining BRDs)

- Week 26 (Jul 31): Program closeout; all 69 BRDs delivered to SI and OCM

Week 26: Closeout & Handoff (Jul 28 - Jul 31, 2026)

Activities:

- Final SI handoff meeting (present requirements, answer questions)

- OCM/Business Readiness handoff (BRDs for training development)

- Archive all materials in SharePoint

- Conduct team retrospective (lessons learned)

- Prepare final program report for SCE PMO

- Celebrate! 🎉

Deliverables:

- 69 approved BRDs

- 69 As-Is flows

- 69 To-Be flows

- 69 Master Requirements Workbooks (each containing business requirements, performance requirements, UAEs, solution requirements, auto-calculated traceability, and gap analysis)

- Solution requirements usage tracker (shows which of SCE's 3000 are used by which L3 processes, identifies orphaned requirements)

- Knowledge repository (enhanced with SCE-specific materials)

- Two-layer requirements model documentation for SI and OCM teams

- Master Requirements Workbook maintenance guide for SI

XIII. SUCCESS CRITERIA

Program succeeds if:

✅ Delivery: All 69 BRDs completed and approved by Jul 31, 2026

✅ Quality:

- <20% of BRDs require major client rework

- 90% of requirements pass SI review without clarification

✅ Efficiency:

- Total effort consumed ≤ 4,894 hours (within budget)

- Average cycle time per BRD ≤ 62 hours

✅ Client Satisfaction:

- SCE stakeholders rate BRD quality ≥4/5 in post-program survey

- Workshops rated as productive and well-facilitated

✅ SI Readiness:

- Requirements handoff enables SI to begin design without delays

- Traceability is clear and complete

CONTACT & SUPPORT

Program Leadership:

- BPD Manager: [Your Name]

- Engagement Manager: Tony (You)

- SCE PMO Lead: [TBD]

Questions or Issues:

- Slack Channel: #ami-brd-factory

- Weekly Office Hours: Fridays 2-3pm PT

- Escalation: Email engagement manager

Document Version: 1.0
Last Updated: JANUARY 5, 2025
Next Review: February 1, 2026 (after team onboarding)

CLOSING THOUGHTS

This factory-line approach transforms BRD development from a sequential, analyst-heavy process into a highly parallelized, AI-assisted production system. The keys to success are:

- Embrace AI for first drafts — but validate rigorously with human expertise

- Absorb wait times — never let client review cycles create idle time

- Batch relentlessly — workshops, reviews, approvals

- Maintain quality gates — speed without quality is failure

- Measure and improve — use metrics to refine the factory continuously

With disciplined execution, this team can deliver 69 high-quality BRDs in 6 months — an ambitious goal made achievable through smart automation and factory-line thinking.

XIV. APPENDICES

APPENDIX A: AI AUTOMATION PROMPTS

This appendix contains all AI prompts used throughout the 13-stage BRD factory-line procedure. Each prompt is referenced in the main procedure by its appendix number (e.g., "See Appendix A.1.3").

Overview: AI Role in BRD Development

AI is a force multiplier for synthesis, formatting, and consistency - NOT a replacement for gathering actual information from SCE stakeholders.

The Pattern:

- Humans gather information (interviews, workshops, client feedback)

- AI synthesizes and formats (turns notes into structured content)

- Humans validate and refine (ensure accuracy and quality)

Never use AI to:

- Invent SCE-specific process details we haven't verified

- Create requirements without tracing to actual business needs

- Make up stakeholder positions or decisions

- Generate content that contradicts what SCE told us

Always use AI to:

- Structure and synthesize interview notes into coherent narratives

- Generate first-draft requirements from validated capabilities

- Incorporate workshop feedback into BRD sections

- Check consistency and flag quality issues

- Format and polish professional deliverables

AI Tool Configuration

Primary Tool: Microsoft Copilot (ChatGPT 4+ or Claude) via M365 tenant

Setup Requirements:

- Create dedicated SharePoint site: "AMI 2.0 Knowledge Repository"

- Upload all reference materials:

  - Previous AMI BRDs and requirements (PDFs, Excel)

  - Visio process flow library (100+ flows)

  - SCE ConOps and AMI 1.0 documentation

  - Industry standards and best practices

- Tag all documents with metadata: L1 category, L2 category, utility name, year

- Grant Copilot access permissions to repository

Best Practices:

- Always review AI output for accuracy against source material

- Never accept AI-generated content without human validation

- Use AI to accelerate, not replace, human judgment

- Iterate prompts if output quality is poor

- Document any prompt modifications that improve results

STAGE 1: Current State Process Mapping

A.1.3: As-Is Process Narrative Synthesis

Activity: AI-Assisted Synthesis (Stage 1, Activity 3)
When to Use: After conducting stakeholder interviews
Duration: Part of 3-hour synthesis activity

Prerequisites:

- Raw interview notes or Copilot transcription from SCE SME interviews

- SCE AMI 1.0 documentation (if available)

- Similar process from another utility (for structure reference only)

Prompt:

I conducted stakeholder interviews about SCE's current [L3 Process Name].

INTERVIEW NOTES (PRIMARY SOURCE):

[Paste raw interview notes or Copilot transcription]

SCE AMI 1.0 DOCUMENTATION (SUPPORTING):

[Attach or paste relevant sections]

SIMILAR PROCESS FROM ANOTHER UTILITY (STRUCTURE REFERENCE ONLY):

[Attach Visio/PPT for format guidance - NOT for content]

Please synthesize the interview notes into a coherent As-Is process narrative.

Base your narrative PRIMARILY on what SCE told us in the interviews - the other

utility's process is just to understand how to structure the output.

Include:

1. Trigger/initiating event (exactly as SCE described it)

2. Key activities (5-10 steps in the sequence SCE follows)

3. Decision points (where SCE makes choices/branches)

4. System interactions (use SCE's system names in [brackets])

5. Handoffs to other teams (as SCE described them)

6. Final output/deliverable

7. Pain points and inefficiencies (flagged clearly with 'PAIN POINT:' prefix)

8. Current workarounds or manual processes

Format as numbered steps. Use professional utility operations language but stay

true to how SCE actually does this today - don't make it sound better than it is.

Expected Output:

- As-Is process narrative (1-2 pages)

- Numbered steps in professional language

- Pain points clearly flagged with 'PAIN POINT:' prefix

- Based on actual SCE interview content

Quality Check:

- Verify narrative matches interview notes

- Ensure all pain points from interviews are captured

- Confirm SCE-specific details (not generic utility language)

- Validate system names match SCE's actual systems

STAGE 2: Repository Mining & Solution Requirements Filtering

A.2.1: Solution Requirements Filtering

Activity: Filter SCE's Solution Requirements (Stage 2, Activity 3, Step 3.2)
When to Use: After identifying systems involved from As-Is flow
Duration: Part of 1.5-hour filtering activity

Prerequisites:

- As-Is flow from Stage 1 showing which systems are involved

- Access to SCE's full solution requirements library (~3,000 requirements)

- L3 process details from inventory

Prompt:

I need to identify which of SCE's solution requirements are relevant to [L3 Process Name].

L3 PROCESS DETAILS:

- Process Name: [e.g., Off-Cycle Billing (Register Billed – Electric)]

- Process Objective: [from inventory]

- Systems Involved: [from As-Is flow - e.g., CSS, MDMS, HES, Salesforce]

- Key Process Steps: [summarize 5-8 main steps from As-Is flow]

SCE SOLUTION REQUIREMENTS TO REVIEW:

[Attach relevant Excel sections - e.g., MDMS meter reading requirements, HES on-demand reads]

TASK:

Review each solution requirement and classify:

1. DIRECTLY RELEVANT: This requirement enables a specific step in this L3 process

- Which process step does it support?

- What business outcome does it enable?

2. INDIRECTLY RELEVANT: This requirement supports the process but isn't core to it

- How does it provide supporting capability?

3. NOT RELEVANT: This requirement belongs to a different L3 process

- Why isn't it applicable here?

OUTPUT FORMAT:

Excel table:

| Solution Req ID | Requirement Text | Relevance | Supports Process Step | Business Outcome | Notes |

CLASSIFICATION EXAMPLES:

DIRECTLY RELEVANT:

'MDMS shall return register reads within 2 minutes of request'

→ Directly supports process step 'Retrieve read from MDMS for off-cycle billing'

→ Enables business outcome 'Complete off-cycle bill within 10 minutes'

INDIRECTLY RELEVANT:

'MDMS shall maintain 40 months of interval data retention'

→ Indirectly supports off-cycle billing (data must exist to be retrieved)

→ But retention duration isn't core to the off-cycle billing workflow

NOT RELEVANT:

'MDMS shall aggregate transformer loading data'

→ Not relevant to off-cycle billing (this is a grid operations function)

→ Belongs to 'Monitor Feeder and Transformer Loading' L3 process

Focus on precision - when uncertain, mark INDIRECTLY and explain.

Expected Output:

- Excel table with 20-50 solution requirements classified

- Each requirement has relevance classification and rationale

- Directly relevant requirements mapped to specific process steps

Quality Check:

- Spot-check 10-15 "Directly Relevant" classifications

- Verify "Not Relevant" requirements truly don't apply

- Ensure output is 20-50 requirements (if significantly more/less, review filtering logic)

A.2.2: Capabilities Extraction from Repository

Activity: Draft Capabilities (Stage 2, Activity 2)
When to Use: When drafting Section 1.2.1 capabilities list
Duration: Part of 1-hour drafting activity

Prerequisites:

- L3 process name and description from inventory

- Similar processes from repository (other utilities)

- As-Is flow from Stage 1

- Industry best practices or standards

Prompt:

I need to define business capabilities for [L3 Process Name].

L3 PROCESS DESCRIPTION:

[Paste from inventory or As-Is summary]

SIMILAR PROCESSES FROM REPOSITORY:

[Attach 2-3 BRDs from other utilities showing their capabilities sections]

INDUSTRY CONTEXT:

[Any relevant standards or best practices]

TASK:

Generate 10-15 business capabilities that this process must deliver.

CAPABILITY FORMAT:

"Ability to [action verb] [object] [context/constraint]"

REQUIREMENTS:

1. Start each with "Ability to"

2. Be outcome-focused (what the process achieves), not task-focused (what people do)

3. Keep each capability to 1 sentence

4. Ensure capabilities are measurable

5. Align with modern AMI 2.0 environment (leverage automation where possible)

6. Flag any that require SCE-specific validation with [VALIDATE WITH SCE]

EXAMPLES:

✅ GOOD:

"Ability to retrieve validated meter reads from MDMS within 5 minutes for off-cycle billing scenarios"

(Specific, measurable, outcome-focused)

❌ BAD:

"Ability to improve billing processes"

(Vague, not measurable, not specific)

✅ GOOD:

"Ability to automatically route failed read requests to field investigation queue with priority classification [VALIDATE WITH SCE: priority rules]"

(Specific, flags SCE input needed)

Generate 10-15 capabilities now.

Expected Output:

- 10-15 capabilities in "Ability to..." format

- Mix of automated and manual process capabilities

- Some flagged with [VALIDATE WITH SCE] for confirmation

Quality Check:

- Each starts with "Ability to"

- Each is specific and measurable

- Capabilities cover end-to-end process

- Appropriate use of [VALIDATE WITH SCE] flags

STAGE 4: To-Be Process Design

A.4.1: To-Be Process Design from As-Is

Activity: To-Be Flow Design (Stage 4, Activity 1)
When to Use: After gathering validated inputs from Stages 1-3
Duration: Part of 4-hour design activity

Prerequisites:

- As-Is flow (narrative and Visio) from Stage 1

- Pain points summary from Stage 1 interviews

- Filtered solution requirements from Stage 2 (20-50 requirements)

- Validated capabilities from Stage 3

Prompt:

I have the As-Is process flow that needs to be redesigned for an AMI 2.0 environment.

AS-IS PROCESS:

[Attach or paste As-Is narrative and Visio screenshot]

CURRENT PAIN POINTS (from Stage 1 interviews):

[List top 5-7 pain points identified by SCE SMEs]

Example:

- Manual MDMS lookups take 30-45 minutes per request

- No visibility into read quality without separate MDMS login

- Frequent timeouts when requesting on-demand reads

- Manual re-entry of reads into CSS causes transcription errors

AMI 2.0 SYSTEM CAPABILITIES (from filtered solution requirements Stage 2):

[List 5-10 key solution requirements that enable automation]

Example:

- MDMS-REQ-047: MDMS shall return reads within 2 minutes

- HES-REQ-019: HES shall support on-demand read requests

- CSS-REQ-103: CSS shall auto-ingest MDMS read responses

- MDMS-REQ-052: MDMS shall provide read quality codes

- BPEM-REQ-015: BPEM shall support automated work order creation

VALIDATED CAPABILITIES (from Stage 3):

[List business capabilities confirmed by SCE]

TASK:

Redesign this process to leverage AMI 2.0 automation and address the pain points.

TO-BE DESIGN REQUIREMENTS:

1. Eliminate or reduce manual steps where solution requirements support automation

2. Address each pain point explicitly (reference solution requirement that fixes it)

3. Maintain necessary human oversight (don't automate critical decisions without approval gates)

4. Add exception handling (what happens when automation fails?)

5. Preserve compliance requirements (regulatory, policy, audit needs)

6. Show realistic improvement metrics (e.g., "Reduced from 2 hours to 10 minutes via MDMS-REQ-047")

OUTPUT FORMAT:

Numbered process steps (same format as As-Is):

1. [Triggering event]

2. [Step 2 - show if automated or manual]

- System: [CSS/MDMS/HES/etc.]

- Automation: [Reference solution requirement if automated]

3. [Decision point - if/then logic]

4. [Exception handling - what if step 3 fails?]

...

[Final output/deliverable]

For each automated step, cite the solution requirement that enables it.

For each manual step that remains, explain why it can't be automated.

IMPROVEMENT SUMMARY:

Create a table showing:

| Pain Point | How To-Be Addresses It | Solution Req | Expected Benefit |

CONSTRAINTS:

- Only leverage capabilities confirmed in SCE's solution requirements

- If solution requirement doesn't exist for a desired automation, flag it with [GAP]

- Maintain manual override capability for exceptions

- Always include fallback for system failures

Generate the To-Be process narrative now.

Expected Output:

- Complete To-Be process narrative with numbered steps

- Each automated step references supporting solution requirement

- Manual steps explained (why automation not possible)

- Improvement summary table showing pain point resolution

- Realistic benefit quantification

Quality Check:

- Every automation claim backed by solution requirement

- All As-Is pain points addressed in To-Be

- Exception handling defined for critical steps

- Improvement metrics are realistic and measurable

- No invented capabilities (all based on solution requirements)

STAGE 7: Process Flow Refinement

A.7.2: To-Be Narrative Update from Workshop Feedback

Activity: Update To-Be Flow (Stage 7, Activity 1, Step 2)
When to Use: After Stage 6 Process Validation Workshop
Duration: Part of 1-hour narrative update activity

Prerequisites:

- Current To-Be narrative from Stage 4

- Change log from Stage 6 workshop

- Workshop notes with all stakeholder feedback

Prompt:

I have a To-Be process narrative that needs to be updated based on workshop feedback.

CURRENT TO-BE NARRATIVE:

[Paste current narrative]

WORKSHOP CHANGES REQUESTED:

[Paste change log from Stage 6]

Example changes:

- Change #1: Add validation of account status before requesting read

- Change #2: Add priority flag for urgent requests in Step 4

- Change #3: Clarify exception handling when MDMS times out

- Change #4: Add notification to Field Ops when read fails

TASK:

Update the To-Be process narrative to incorporate all workshop changes.

REQUIREMENTS:

- Maintain numbered step format

- Keep professional utility operations language

- Show which steps are automated vs. manual

- Include all decision points (if/then logic)

- Document exception handling clearly

- Reference systems in [brackets]

- Maintain same level of detail as before

- Ensure changes are integrated smoothly (narrative flows logically)

For each change, ensure:

- New steps are inserted in the right sequence

- Modified steps retain their context

- Exception paths are clearly documented

- Handoffs between roles are explicit

OUTPUT:

Updated To-Be process narrative with all workshop changes incorporated.

Expected Output:

- Updated To-Be narrative with all changes incorporated

- Numbered steps in consistent format

- Changes integrated smoothly into existing flow

Quality Check:

- All changes from change log incorporated

- Narrative still flows logically

- No contradictions with solution requirements

- Professional language maintained

STAGE 8: Requirements Generation

The prompts for Stage 8 are already referenced inline in the procedure. They include:

- A.8.1: User Journey Mapping

- A.8.2A: Business Requirements Generation (Exploratory)

- A.8.2B: Business Requirements Traceability Mapping

- A.8.3: User Acceptance Expectations Generation

- A.8.4: Performance Requirements Generation

- A.8.5: Gap Analysis and Categorization

- A.8.6: Master Requirements Workbook Structure

These are detailed extensively in the existing appendix content and are cross-referenced properly in the main procedure.

STAGE 12: Client Review & Rework

A.12.1: Address Client Review Comments

Activity: Incorporate Client Feedback (Stage 12, Activity 2)
When to Use: After receiving client review comments
Duration: Part of comment disposition activity

Prerequisites:

- Client review comments/feedback

- Original BRD sections

- Master Requirements Workbook

Prompt:

I have client review comments on a BRD. Help me address them:

Current requirement: [paste requirement]

Client comment: [paste exact comment]

Example: 'This requirement is too vague. We need specific SLA targets and escalation procedures.'

TASK:

Provide 3 alternative formulations that address the client's concern while maintaining:

- Clear fit criterion (testable and measurable)

- Traceability to solution requirements

- Proper requirement structure

For each option, explain the trade-offs and recommend which is best.

Expected Output:

- 3 alternative requirement formulations

- Trade-offs explained for each option

- Recommendation with rationale

A.12.2: BRD Quality Review

Activity: Final Quality Check (Stage 12, Activity 3)
When to Use: Before resubmitting BRD to client
Duration: Part of final quality check

Prerequisites:

- Updated BRD sections after incorporating client comments

- Master Requirements Workbook

Prompt:

Review this BRD for common quality issues:

[Paste sections 4.1 and 4.2]

Check for:

- Duplicate requirement IDs

- Missing fit criteria

- Inconsistent terminology

- Requirements that contradict each other

- Ambiguous language ('user-friendly,' 'efficient')

- Traceability gaps

- Formatting inconsistencies

Provide a quality report with specific line items to fix, prioritized by severity:

- CRITICAL: Must fix before submission

- IMPORTANT: Should fix for quality

- MINOR: Nice to have improvements

Expected Output:

- Quality report with specific issues identified

- Line-by-line feedback for corrections

- Prioritized by severity (critical, important, minor)

END OF APPENDIX A